## Effort logged
Product | Project | Iteration | Story Id | Story | Story State (current) | Story Responsibles | Story labels | Story Description | Story points | Story value | Story depends on | Story required by | Task Id | Task | Task State (current) | Task Responsibles | Task Description | Logged effort (hours) | Logged effort comment | User who logged the effort | Logged effort date | Estimated effort left (hours) | Original Estimate (hours) | Leaf Story | Iteration rank | Backlog rank | Hierarchy position | Parent stories
[18 empty] | 2 |  | Samuel Marisa | 2013-09-05 14:12
[13 empty] | 586066 | Peer group testing | Not Started | Matias Pitkänen |  | 3.5 |  | Matias Pitkänen | 2016-03-18 17:45
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518994 | Analyse projects | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | scheduling | Teemu Blomqvist | 2015-10-08 11:30 | 0 | 70
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518994 | Analyse projects | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 4 | skype with Takala plus discussions | Tuomo Perä | 2015-10-07 11:29 | 0 | 70
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518994 | Analyse projects | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2.5 | meeting Darst of CSG | Matias Pitkänen | 2015-10-07 11:29 | 0 | 70
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518994 | Analyse projects | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 4 | skype with Takala plus discussions | Teemu Blomqvist | 2015-10-07 11:29 | 0 | 70
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518994 | Analyse projects | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2.5 | meeting Darst of CSG | Joona Marjakangas | 2015-10-07 11:29 | 0 | 70
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518994 | Analyse projects | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 4 | skype with Takala plus discussions | Iiro Tähkä | 2015-10-07 11:29 | 0 | 70
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518994 | Analyse projects | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | studying about projects | Iiro Tähkä | 2015-10-05 11:38 | 0 | 70
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518994 | Analyse projects | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 4 | skype with Takala plus discussions | Samuel Marisa | 2015-10-07 11:29 | 0 | 70
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518994 | Analyse projects | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2.5 | meeting Jelena plus discussion | Samuel Marisa | 2015-10-09 11:32 | 0 | 70
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518994 | Analyse projects | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 4 | skype with Takala plus discussions | Joona Marjakangas | 2015-10-07 11:29 | 0 | 70
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518994 | Analyse projects | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | studying about projects | Teemu Blomqvist | 2015-10-05 11:38 | 0 | 70
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518994 | Analyse projects | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | studying about projects | Juho Pekkinen | 2015-10-05 11:38 | 0 | 70
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518994 | Analyse projects | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | studying about projects | Joona Marjakangas | 2015-10-05 11:38 | 0 | 70
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518994 | Analyse projects | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2.5 | meeting Darst of CSG | Samuel Marisa | 2015-10-07 11:29 | 0 | 70
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518994 | Analyse projects | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 4 | skype with Takala plus discussions | Juho Pekkinen | 2015-10-07 11:29 | 0 | 70
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518994 | Analyse projects | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | studying about projects | Matias Pitkänen | 2015-10-05 11:38 | 0 | 70
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518994 | Analyse projects | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 4 | skype with Takala plus discussions | Matias Pitkänen | 2015-10-07 11:29 | 0 | 70
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518994 | Analyse projects | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | scheduling | Juho Pekkinen | 2015-10-08 11:30 | 0 | 70
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518994 | Analyse projects | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | scheduling | Iiro Tähkä | 2015-10-08 11:30 | 0 | 70
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518994 | Analyse projects | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2.5 | meeting Jelena plus discussion | Joona Marjakangas | 2015-10-09 11:32 | 0 | 70
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518994 | Analyse projects | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2.5 | meeting Darst of CSG | Tuomo Perä | 2015-10-07 11:29 | 0 | 70
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518994 | Analyse projects | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | scheduling | Tuomo Perä | 2015-10-08 11:30 | 0 | 70
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518994 | Analyse projects | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | scheduling | Matias Pitkänen | 2015-10-08 11:30 | 0 | 70
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518994 | Analyse projects | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2.5 | meeting Jelena plus discussion | Teemu Blomqvist | 2015-10-09 11:32 | 0 | 70
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518994 | Analyse projects | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | scheduling | Samuel Marisa | 2015-10-08 11:30 | 0 | 70
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518994 | Analyse projects | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2.5 | meeting Darst of CSG | Teemu Blomqvist | 2015-10-07 11:29 | 0 | 70
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518994 | Analyse projects | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | studying about projects | Tuomo Perä | 2015-10-05 11:38 | 0 | 70
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518994 | Analyse projects | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | scheduling | Joona Marjakangas | 2015-10-08 11:30 | 0 | 70
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518994 | Analyse projects | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 8 | studying projects | Samuel Marisa | 2015-10-05 11:27 | 0 | 70
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518994 | Analyse projects | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2.5 | meeting Jelena plus discussion | Tuomo Perä | 2015-10-09 11:32 | 0 | 70
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518964 | Build team | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | first team meeting | Teemu Blomqvist | 2015-09-29 11:08 | 0 | 65
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518964 | Build team | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | working on cv | Joona Marjakangas | 2015-09-06 11:13 | 0 | 65
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518964 | Build team | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | working on cv | Juho Pekkinen | 2015-09-06 11:13 | 0 | 65
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518964 | Build team | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | working on cv | Teemu Blomqvist | 2015-09-06 11:13 | 0 | 65
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518964 | Build team | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | working on cv | Matias Pitkänen | 2015-09-06 11:13 | 0 | 65
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518964 | Build team | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 17 | working on cv | Samuel Marisa | 2015-10-04 11:12 | 0 | 65
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518964 | Build team | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | working on cv | Tuomo Perä | 2015-09-06 11:13 | 0 | 65
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518964 | Build team | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | first team meeting | Joona Marjakangas | 2015-09-29 11:08 | 0 | 65
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518964 | Build team | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 4 | first team meeting | Samuel Marisa | 2015-09-29 11:08 | 0 | 65
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518964 | Build team | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 16 | prepare git challenge, revision & study | Samuel Marisa | 2015-10-02 11:10 | 0 | 65
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518964 | Build team | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | first team meeting | Tuomo Perä | 2015-09-29 11:08 | 0 | 65
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518964 | Build team | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | first team meeting | Juho Pekkinen | 2015-09-29 11:08 | 0 | 65
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518964 | Build team | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | first team meeting | Iiro Tähkä | 2015-09-29 11:08 | 0 | 65
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518964 | Build team | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | first team meeting | Matias Pitkänen | 2015-09-29 11:08 | 0 | 65
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518964 | Build team | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | working on cv | Iiro Tähkä | 2015-09-06 11:13 | 0 | 65
NeronetTrainer | Version 1 | Presprint | [10 empty] | 519000 | Choose project | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | project decision | Iiro Tähkä | 2015-10-11 11:40 | 0 | 22
NeronetTrainer | Version 1 | Presprint | [10 empty] | 519000 | Choose project | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | project decision | Tuomo Perä | 2015-10-11 11:40 | 0 | 22
NeronetTrainer | Version 1 | Presprint | [10 empty] | 519000 | Choose project | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | project decision | Matias Pitkänen | 2015-10-11 11:40 | 0 | 22
NeronetTrainer | Version 1 | Presprint | [10 empty] | 519000 | Choose project | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | project decision | Juho Pekkinen | 2015-10-11 11:40 | 0 | 22
NeronetTrainer | Version 1 | Presprint | [10 empty] | 519000 | Choose project | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | project decision | Samuel Marisa | 2015-10-11 11:40 | 0 | 22
NeronetTrainer | Version 1 | Presprint | [10 empty] | 519000 | Choose project | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | project decision | Teemu Blomqvist | 2015-10-11 11:40 | 0 | 22
NeronetTrainer | Version 1 | Presprint | [10 empty] | 519000 | Choose project | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 4 | init emails to POs | Samuel Marisa | 2015-10-11 11:41 | 0 | 22
NeronetTrainer | Version 1 | Presprint | [10 empty] | 519000 | Choose project | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | project decision | Joona Marjakangas | 2015-10-11 11:40 | 0 | 22
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518962 | Recruit team members | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | scheduling the team meetup | Tuomo Perä | 2015-09-22 11:04 | 0 | 14
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518962 | Recruit team members | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | scheduling the team meetup | Iiro Tähkä | 2015-09-22 11:04 | 0 | 14
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518962 | Recruit team members | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | scheduling the team meetup | Juho Pekkinen | 2015-09-22 11:04 | 0 | 14
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518962 | Recruit team members | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | scheduling the team meetup | Matias Pitkänen | 2015-09-22 11:04 | 0 | 14
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518962 | Recruit team members | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | recruiting | Samuel Marisa | 2015-09-21 11:05 | 0 | 14
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518962 | Recruit team members | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | scheduling the team meetup | Samuel Marisa | 2015-09-22 11:04 | 0 | 14
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518962 | Recruit team members | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | recruiting | Samuel Marisa | 2015-09-21 11:03 | 0 | 14
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518962 | Recruit team members | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | scheduling the team meetup | Joona Marjakangas | 2015-09-22 11:04 | 0 | 14
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518962 | Recruit team members | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | scheduling the team meetup | Teemu Blomqvist | 2015-09-22 11:04 | 0 | 14
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518962 | Recruit team members | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | recruiting | Samuel Marisa | 2015-09-22 11:04 | 0 | 14
NeronetTrainer | Version 1 | Sprint 0 | [15 empty] | 1 |  | Samuel Marisa | 2015-10-24 11:34
NeronetTrainer | Version 1 | Sprint 0 | [15 empty] | 3 |  | Teemu Blomqvist | 2015-10-24 11:35
NeronetTrainer | Version 1 | Sprint 0 | [15 empty] | 3 |  | Tuomo Perä | 2015-10-24 11:35
NeronetTrainer | Version 1 | Sprint 0 | [15 empty] | 0.5 |  | Joona Marjakangas | 2015-10-23 20:29
NeronetTrainer | Version 1 | Sprint 0 | [15 empty] | 0.5 |  | Joona Marjakangas | 2015-10-23 22:29
NeronetTrainer | Version 1 | Sprint 0 | [15 empty] | 1 |  | Samuel Marisa | 2015-10-16 16:02
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519342 | Communicate the process and schedule | Done | Samuel Marisa |  | 0.45 | sent emails about the last week | Samuel Marisa | 2015-11-08 15:29 | 0 | 3
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519342 | Communicate the process and schedule | Done | Samuel Marisa |  | 0.5 | Explained schedule in meeting | Samuel Marisa | 2015-11-06 20:36 | 0 | 3
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519342 | Communicate the process and schedule | Done | Samuel Marisa |  | 1.5 | specified meetings and their agendas | Samuel Marisa | 2015-11-08 15:02 | 0 | 3
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519342 | Communicate the process and schedule | Done | Samuel Marisa |  | 0.66667 | emailed the team and the interviewee | Samuel Marisa | 2015-11-05 21:40 | 0 | 3
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519035 | Develop a basic prototype | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3.5 | sketched neroman | Joona Marjakangas | 2015-11-07 21:21 | 0 | 30
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519035 | Develop a basic prototype | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.5 | directed teamwork | Samuel Marisa | 2015-11-07 18:25 | 0 | 30
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519035 | Develop a basic prototype | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3.5 | Prototype design | Iiro Tähkä | 2015-11-06 19:53 | 0 | 30
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519035 | Develop a basic prototype | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | directed teamwork | Samuel Marisa | 2015-11-07 20:45 | 0 | 30
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519035 | Develop a basic prototype | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 4 | worked during Wedshop | Joona Marjakangas | 2015-11-11 20:09 | 0 | 30
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519035 | Develop a basic prototype | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 6 | worked during Wedshop | Samuel Marisa | 2015-11-11 20:06 | 0 | 30
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519035 | Develop a basic prototype | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.75 | Investigated virtualenv and python 3.5 | Iiro Tähkä | 2015-11-07 20:26 | 0 | 30
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519035 | Develop a basic prototype | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.5 | consulted and directed the work | Samuel Marisa | 2015-11-06 20:00 | 0 | 30
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519035 | Develop a basic prototype | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 6 | worked during Wedshop | Tuomo Perä | 2015-11-11 20:06 | 0 | 30
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519035 | Develop a basic prototype | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 5 | worked during Wedshop | Iiro Tähkä | 2015-11-11 20:08 | 0 | 30
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519035 | Develop a basic prototype | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.65 | working on how to properly setup a Python project | Samuel Marisa | 2015-11-08 17:08 | 0 | 30
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519035 | Develop a basic prototype | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 6 | worked during Wedshop | Teemu Blomqvist | 2015-11-11 20:06 | 0 | 30
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519035 | Develop a basic prototype | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3.5 | Prototype design | Joona Marjakangas | 2015-11-06 19:53 | 0 | 30
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519035 | Develop a basic prototype | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | sketched nerokid+neromum | Matias Pitkänen | 2015-11-07 20:23 | 0 | 30
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519035 | Develop a basic prototype | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 4 | developed a basic prototype | Samuel Marisa | 2015-11-12 10:58 | 0 | 30
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519035 | Develop a basic prototype | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.5 | discussed the prototype with PO | Samuel Marisa | 2015-11-09 22:42 | 0 | 30
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519035 | Develop a basic prototype | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 6 | worked during Wedshop | Matias Pitkänen | 2015-11-11 20:06 | 0 | 30
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519035 | Develop a basic prototype | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2.5 | developed neroman prototype | Iiro Tähkä | 2015-11-07 20:27 | 0 | 30
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519035 | Develop a basic prototype | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3.5 | scheched nerokid and neromum | Tuomo Perä | 2015-11-07 20:22 | 0 | 30
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519699 | Discuss plans and architecture with systems experts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.5 | Interview with Simo Tuomisto | Joona Marjakangas | 2015-11-06 16:40 | 0 | 9
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519699 | Discuss plans and architecture with systems experts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.5 | Interview with Simo Tuomisto | Teemu Blomqvist | 2015-11-06 16:40 | 0 | 9
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519699 | Discuss plans and architecture with systems experts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.5 | Interview with Simo Tuomisto | Tuomo Perä | 2015-11-06 16:40 | 0 | 9
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519699 | Discuss plans and architecture with systems experts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.5 | Interview with Simo Tuomisto | Iiro Tähkä | 2015-11-06 16:40 | 0 | 9
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519699 | Discuss plans and architecture with systems experts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.5 | Interview with Simo Tuomisto | Matias Pitkänen | 2015-11-06 16:40 | 0 | 9
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519699 | Discuss plans and architecture with systems experts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.5 | Interview with Simo Tuomisto | Samuel Marisa | 2015-11-06 16:40 | 0 | 9
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519034 | Perform a market analysis | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.6 | discussed tools on market | Matias Pitkänen | 2015-11-09 22:37 | 0 | 20
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519034 | Perform a market analysis | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.7 | studied TensorFlow | Samuel Marisa | 2015-11-13 19:00 | 0 | 20
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519034 | Perform a market analysis | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2.5 |  | Matias Pitkänen | 2015-11-06 18:38 | 0 | 20
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519034 | Perform a market analysis | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.5 | consulted and directed the work | Samuel Marisa | 2015-11-06 20:00 | 0 | 20
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519034 | Perform a market analysis | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.7 | studied Blocks | Samuel Marisa | 2015-11-07 19:07 | 0 | 20
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519034 | Perform a market analysis | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.6 | discussed tools on market | Tuomo Perä | 2015-11-09 22:37 | 0 | 20
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519034 | Perform a market analysis | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3.5 |  | Tuomo Perä | 2015-11-06 18:38 | 0 | 20
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519034 | Perform a market analysis | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.6 | discussed tools on market | Pyry Takala | 2015-11-09 22:37 | 0 | 20
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519034 | Perform a market analysis | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.6 | discussed tools on market | Joona Marjakangas | 2015-11-09 22:37 | 0 | 20
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519034 | Perform a market analysis | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.6 | discussed tools on market | Samuel Marisa | 2015-11-09 22:37 | 0 | 20
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 520459 | Prepare an initial backlog for sprint 1 | Done | Pyry Takala, Samuel Marisa |  | 1 | discussed backlog management, made some edits | Pyry Takala | 2015-11-09 22:34 | 0 | 8
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 520459 | Prepare an initial backlog for sprint 1 | Done | Pyry Takala, Samuel Marisa |  | 0.4 | consulted Pyry on terminology | Samuel Marisa | 2015-11-10 15:27 | 0 | 8
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 520459 | Prepare an initial backlog for sprint 1 | Done | Pyry Takala, Samuel Marisa |  | 1 | discussed backlog management, made some edits | Matias Pitkänen | 2015-11-09 22:34 | 0 | 8
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 520459 | Prepare an initial backlog for sprint 1 | Done | Pyry Takala, Samuel Marisa |  | 1 | discussed backlog management, made some edits | Samuel Marisa | 2015-11-09 22:34 | 0 | 8
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 520459 | Prepare an initial backlog for sprint 1 | Done | Pyry Takala, Samuel Marisa |  | 2 | developed the initial backlog draft | Samuel Marisa | 2015-11-08 15:01 | 0 | 8
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 520459 | Prepare an initial backlog for sprint 1 | Done | Pyry Takala, Samuel Marisa |  | 0.8 | updated the backlog, ended sprint 0 | Samuel Marisa | 2015-11-13 23:00 | 0 | 8
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 520459 | Prepare an initial backlog for sprint 1 | Done | Pyry Takala, Samuel Marisa |  | 0.23333 | consulted Pyry | Samuel Marisa | 2015-11-12 11:12 | 0 | 8
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 520459 | Prepare an initial backlog for sprint 1 | Done | Pyry Takala, Samuel Marisa |  | 0.11667 | asked for subscription extension from Agilefant | Samuel Marisa | 2015-11-12 11:19 | 0 | 8
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 520459 | Prepare an initial backlog for sprint 1 | Done | Pyry Takala, Samuel Marisa |  | 1 | discussed backlog management, made some edits | Joona Marjakangas | 2015-11-09 22:34 | 0 | 8
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 520459 | Prepare an initial backlog for sprint 1 | Done | Pyry Takala, Samuel Marisa |  | 1 | discussed backlog management, made some edits | Tuomo Perä | 2015-11-09 22:34 | 0 | 8
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | artifacts workshop | Samuel Marisa | 2015-10-24 12:09 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | Slurm & Triton workshop | Iiro Tähkä | 2015-10-25 12:11 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 7 | Frifury and First meeting with PO | Joona Marjakangas | 2015-10-30 12:14 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3.5 | artifacts workshop | Samuel Marisa | 2015-10-23 12:08 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | artifacts workshop | Tuomo Perä | 2015-10-24 12:09 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | tech workshop, state-of-the-art | Teemu Blomqvist | 2015-10-25 12:10 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 7 | Frifury and First meeting with PO | Iiro Tähkä | 2015-10-30 12:14 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | Wedshop on team practices, time tracking, project evaluation and architecture | Matias Pitkänen | 2015-11-04 12:19 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | tech workshop, state-of-the-art | Iiro Tähkä | 2015-10-25 12:10 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | Wedshop on team practices, time tracking, project evaluation and architecture | Joona Marjakangas | 2015-11-04 12:19 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | Slurm & Triton workshop | Matias Pitkänen | 2015-10-25 12:11 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | Wedshop on team practices, time tracking, project evaluation and architecture | Tuomo Perä | 2015-11-04 12:19 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3.5 | artifacts workshop | Matias Pitkänen | 2015-10-23 12:08 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 7 | Frifury and First meeting with PO | Tuomo Perä | 2015-10-30 12:14 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 7 | Frifury and First meeting with PO | Samuel Marisa | 2015-10-30 12:14 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | tech workshop, state-of-the-art | Tuomo Perä | 2015-10-25 12:10 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | Wedshop on artifacts | Iiro Tähkä | 2015-10-28 12:13 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 7 | Frifury and First meeting with PO | Matias Pitkänen | 2015-10-30 12:14 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | Wedshop on team practices, time tracking, project evaluation and architecture | Samuel Marisa | 2015-11-04 12:19 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.5 | organized and cleaned the product backlog | Samuel Marisa | 2015-11-05 12:37 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | tech workshop, state-of-the-art | Samuel Marisa | 2015-10-25 12:10 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3.5 | artifacts workshop | Joona Marjakangas | 2015-10-23 12:08 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | Wedshop on artifacts | Teemu Blomqvist | 2015-10-28 12:13 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | Slurm & Triton workshop | Samuel Marisa | 2015-10-25 12:11 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 17 | work on evaluation, architecture, artifacts, expert interviews | Samuel Marisa | 2015-11-02 12:18 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | Wedshop on artifacts | Tuomo Perä | 2015-10-28 12:13 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 7 | Frifury and First meeting with PO | Teemu Blomqvist | 2015-10-30 12:14 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 8 | work on notes, time tracking, agilefant and team management | Samuel Marisa | 2015-11-05 12:20 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | artifacts workshop | Teemu Blomqvist | 2015-10-24 12:09 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | Wedshop on artifacts | Matias Pitkänen | 2015-10-28 12:13 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | Wedshop on artifacts | Samuel Marisa | 2015-10-28 12:13 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | tech workshop, state-of-the-art | Matias Pitkänen | 2015-10-25 12:10 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | Slurm & Triton workshop | Tuomo Perä | 2015-10-25 12:11 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | Wedshop on artifacts | Joona Marjakangas | 2015-10-28 12:13 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 17 | work on artifacts and tools, management | Samuel Marisa | 2015-10-28 12:16 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | Wedshop on team practices, time tracking, project evaluation and architecture | Iiro Tähkä | 2015-11-04 12:19 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | Wedshop on team practices, time tracking, project evaluation and architecture | Teemu Blomqvist | 2015-11-04 12:19 | 0 | 155
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 523744 | Present sprint 0 results to Coach | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 4.5 | prepared and presented the results | Teemu Blomqvist | 2015-11-13 18:30 | 0 | 27
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 523744 | Present sprint 0 results to Coach | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 4.5 | prepared and presented the results | Joona Marjakangas | 2015-11-13 18:30 | 0 | 27
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 523744 | Present sprint 0 results to Coach | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 4.5 | prepared and presented the results | Samuel Marisa | 2015-11-13 18:30 | 0 | 27
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 523744 | Present sprint 0 results to Coach | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3.5 | prepared and presented the results | Iiro Tähkä | 2015-11-13 18:30 | 0 | 27
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 523744 | Present sprint 0 results to Coach | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 4.5 | prepared and presented the results | Matias Pitkänen | 2015-11-13 18:30 | 0 | 27
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 523744 | Present sprint 0 results to Coach | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 4.5 | prepared and presented the results | Tuomo Perä | 2015-11-13 18:30 | 0 | 27
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 523744 | Present sprint 0 results to Coach | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | reviewed the sprint results | Eero Laukkanen | 2015-11-13 18:30 | 0 | 27
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519001 | Understand and initialize project | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | scheduling | Tuomo Perä | 2015-10-17 11:47 | 0 | 60
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519001 | Understand and initialize project | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | drafts meeting | Teemu Blomqvist | 2015-10-14 11:47 | 0 | 60
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519001 | Understand and initialize project | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | drafts meeting | Joona Marjakangas | 2015-10-14 11:47 | 0 | 60
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519001 | Understand and initialize project | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | drafts meeting | Samuel Marisa | 2015-10-14 11:47 | 0 | 60
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519001 | Understand and initialize project | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | scheduling | Juho Pekkinen | 2015-10-17 11:47 | 0 | 60
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519001 | Understand and initialize project | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | scheduling | Joona Marjakangas | 2015-10-17 11:47 | 0 | 60
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519001 | Understand and initialize project | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | drafts meeting | Matias Pitkänen | 2015-10-14 11:47 | 0 | 60
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519001 | Understand and initialize project | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 36 | studying, coordinating & initializing | Samuel Marisa | 2015-10-13 11:45 | 0 | 60
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519001 | Understand and initialize project | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | scheduling | Samuel Marisa | 2015-10-17 11:47 | 0 | 60
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519001 | Understand and initialize project | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | scheduling | Matias Pitkänen | 2015-10-17 11:47 | 0 | 60
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519001 | Understand and initialize project | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | scheduling | Teemu Blomqvist | 2015-10-17 11:47 | 0 | 60
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519001 | Understand and initialize project | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | scheduling | Iiro Tähkä | 2015-10-17 11:47 | 0 | 60
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523750 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.5 | Daily Scrum and general planning | Iiro Tähkä | 2015-11-20 20:54 | 0 | 16
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523750 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.6 | exchanged general thoughts and feelings | Samuel Marisa | 2015-11-24 20:24 | 0 | 16
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523750 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.5 | Daily Scrum and general planning | Matias Pitkänen | 2015-11-20 20:54 | 0 | 16
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523750 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | general discussion | Joona Marjakangas | 2015-12-04 17:29 | 0 | 16
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523750 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.5 | Planning things to to do and checking tools | Teemu Blomqvist | 2015-11-18 20:55 | 0 | 16
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523750 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | Planning things to to do and checking tools | Samuel Marisa | 2015-11-18 20:55 | 0 | 16
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523750 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.5 | Daily Scrum and general planning | Joona Marjakangas | 2015-11-20 20:54 | 0 | 16
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523750 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.5 | Preparing week's agenda | Joona Marjakangas | 2015-12-01 21:30 | 0 | 16
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523750 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.5 | Daily Scrum and general planning | Tuomo Perä | 2015-11-20 20:54 | 0 | 16
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523750 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | Planning Friday's team meeting and skype with PO | Joona Marjakangas | 2015-11-20 15:00 | 0 | 16
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523750 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | Daily Scrum and general planning | Samuel Marisa | 2015-11-20 20:54 | 0 | 16
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523750 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.5 | Daily Scrum and general planning | Teemu Blomqvist | 2015-11-20 20:54 | 0 | 16
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523750 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.5 | Planning things to to do and checking tools | Joona Marjakangas | 2015-11-18 20:55 | 0 | 16
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523750 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.6 | exchanged general thoughts and feelings | Matias Pitkänen | 2015-11-24 20:24 | 0 | 16
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523750 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 |  | Matias Pitkänen | 2015-12-04 16:30 | 0 | 16
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523750 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | EES2 | Joona Marjakangas | 2015-11-18 20:56 | 0 | 16
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523750 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | Planning the week's work | Joona Marjakangas | 2015-11-17 22:21 | 0 | 16
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523750 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | general discussion | Samuel Marisa | 2015-12-04 16:30 | 0 | 16
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523750 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.5 | Planning things to to do and checking tools | Matias Pitkänen | 2015-11-18 20:55 | 0 | 16
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523750 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.5 | Planning things to to do and checking tools | Iiro Tähkä | 2015-11-18 20:55 | 0 | 16
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523750 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.5 | Planning things to to do and checking tools | Tuomo Perä | 2015-11-18 20:55 | 0 | 16
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523750 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | EES2 | Samuel Marisa | 2015-11-18 20:56 | 0 | 16
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523750 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | Planning the week's work | Samuel Marisa | 2015-11-17 22:21 | 0 | 16
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523750 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | Preparing for progress review | Joona Marjakangas | 2015-11-27 19:00 | 0 | 16
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523750 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2.6 | studied and prepared for sprint planning | Samuel Marisa | 2015-11-14 14:36 | 0 | 16
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523750 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.5 | Consulting Joona on planning | Samuel Marisa | 2015-12-01 21:30 | 0 | 16
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523750 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.5 | sent a farewell email to Juho, registered for the EES | Samuel Marisa | 2015-11-14 16:42 | 0 | 16
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523805 | Learning diary | In Progress | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.5 | Project review 1 learning diary | Matias Pitkänen | 2015-12-03 16:35 | 2 | 6
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523805 | Learning diary | In Progress | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 5 | did my learning diary entry and improved the template | Samuel Marisa | 2015-12-05 22:17 | 2 | 6
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523805 | Learning diary | In Progress | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 |  | Iiro Tähkä | 2015-12-03 16:29 | 2 | 6
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523805 | Learning diary | In Progress | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 |  | Teemu Blomqvist | 2015-12-04 16:36 | 2 | 6
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523746 | Restructuring the project repo | Done |  |  | 2 | refactored the repo regarding sphinx | Samuel Marisa | 2015-12-03 20:30 | 0 | 6
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523746 | Restructuring the project repo | Done |  |  | 1 | cleaned the repo | Samuel Marisa | 2015-12-02 23:08 | 0 | 6
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523746 | Restructuring the project repo | Done |  |  | 2.5 | restructured and updated the repo for sprint 1 | Samuel Marisa | 2015-11-14 19:21 | 0 | 6
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523749 | Setting up a documentation system | Done |  |  | 0.5 | Refactored the documentation system. | Samuel Marisa | 2015-12-03 21:00 | 0 | 4
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523749 | Setting up a documentation system | Done |  |  | 2 | setting up and testing Sphinx | Samuel Marisa | 2015-11-18 19:59 | 0 | 4
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523747 | Setting up a testing framework | Done |  |  | 3 | work on testing | Samuel Marisa | 2015-12-03 15:07 | 0 | 4
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523747 | Setting up a testing framework | Done |  |  | 1 | setting up a basic unit testing system | Samuel Marisa | 2015-11-18 20:00 | 0 | 4
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523747 | Setting up a testing framework | Done |  |  | 1 | work on the execution environment | Samuel Marisa | 2015-11-25 19:40 | 0 | 4
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523745 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | planned the sprint | Samuel Marisa | 2015-11-16 14:06 | 0 | 14
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523745 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | planned the sprint | Tuomo Perä | 2015-11-16 14:06 | 0 | 14
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523745 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | planned the sprint | Joona Marjakangas | 2015-11-16 14:06 | 0 | 14
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523745 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | planned the sprint | Matias Pitkänen | 2015-11-16 14:06 | 0 | 14
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523745 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.7 | discussed the scope of the sprint and work schedule | Joona Marjakangas | 2015-11-24 20:23 | 0 | 14
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523745 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | planned the sprint | Pyry Takala | 2015-11-16 14:06 | 0 | 14
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523745 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.7 | discussed the scope of the sprint and work schedule | Samuel Marisa | 2015-11-24 20:23 | 0 | 14
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523745 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | planned the sprint | Teemu Blomqvist | 2015-11-16 14:06 | 0 | 14
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523752 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.2 | Finished the retrospective | Samuel Marisa | 2015-12-04 18:15 | 0 | 6
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523752 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.2 | Finished the retrospective | Iiro Tähkä | 2015-12-04 18:15 | 0 | 6
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523752 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | Retrospective | Samuel Marisa | 2015-12-04 17:00 | 0 | 6
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523752 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 |  | Teemu Blomqvist | 2015-12-04 16:37 | 0 | 6
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523752 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 |  | Iiro Tähkä | 2015-12-04 16:32 | 0 | 6
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523752 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.2 | Finished the retrospective | Teemu Blomqvist | 2015-12-04 18:15 | 0 | 6
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523752 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.2 | Finished the retrospective | Matias Pitkänen | 2015-12-04 18:15 | 0 | 6
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523752 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 |  | Matias Pitkänen | 2015-12-04 16:29 | 0 | 6
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523752 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.2 | Finished the retrospective | Joona Marjakangas | 2015-12-04 18:15 | 0 | 6
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523752 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | Finished the retrospective | Tuomo Perä | 2015-12-04 18:15 | 0 | 6
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523752 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | Sprint 1 retrospective | Joona Marjakangas | 2015-12-04 17:28 | 0 | 6
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523751 | Sprint review | Done | Eero Laukkanen, Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 5 | Prepared for the demo | Teemu Blomqvist | 2015-12-03 16:36 | 0 | 22
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523751 | Sprint review | Done | Eero Laukkanen, Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | Held the sprint review | Eero Laukkanen | 2015-12-04 18:00 | 0 | 22
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523751 | Sprint review | Done | Eero Laukkanen, Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | Held the sprint review | Teemu Blomqvist | 2015-12-04 18:00 | 0 | 22
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523751 | Sprint review | Done | Eero Laukkanen, Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 8 | preparing artifacts | Joona Marjakangas | 2015-12-02 22:00 | 0 | 22
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523751 | Sprint review | Done | Eero Laukkanen, Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.3333 | fixed minor problems in artifacts, updated the stable branch | Samuel Marisa | 2015-12-04 23:47 | 0 | 22
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523751 | Sprint review | Done | Eero Laukkanen, Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | Held the sprint review | Joona Marjakangas | 2015-12-04 18:00 | 0 | 22
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523751 | Sprint review | Done | Eero Laukkanen, Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | preparing the submission | Samuel Marisa | 2015-12-03 18:07 | 0 | 22
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523751 | Sprint review | Done | Eero Laukkanen, Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | Held the sprint review | Matias Pitkänen | 2015-12-04 18:00 | 0 | 22
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523751 | Sprint review | Done | Eero Laukkanen, Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.6 | reviewed the presentation and refactored notes | Samuel Marisa | 2015-12-04 22:27 | 0 | 22
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523751 | Sprint review | Done | Eero Laukkanen, Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | Held the sprint review | Tuomo Perä | 2015-12-04 18:00 | 0 | 22
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523751 | Sprint review | Done | Eero Laukkanen, Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | developing the presentation | Samuel Marisa | 2015-12-02 21:43 | 0 | 22
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523751 | Sprint review | Done | Eero Laukkanen, Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | Held the sprint review | Iiro Tähkä | 2015-12-04 18:00 | 0 | 22
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523751 | Sprint review | Done | Eero Laukkanen, Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 5.5 | Preparing for sprint 1 review | Joona Marjakangas | 2015-12-03 19:30 | 0 | 22
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523751 | Sprint review | Done | Eero Laukkanen, Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | Prepared for the demo | Iiro Tähkä | 2015-12-03 16:31 | 0 | 22
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523751 | Sprint review | Done | Eero Laukkanen, Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | Held the sprint review | Samuel Marisa | 2015-12-04 18:00 | 0 | 22
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523751 | Sprint review | Done | Eero Laukkanen, Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | Held the sprint review | Pyry Takala | 2015-12-04 18:00 | 0 | 22
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523748 | Testing Neronet in Triton | Done |  |  | 2.5167 | tested on Triton and Aalto Kosh | Samuel Marisa | 2015-12-03 23:01 | 0 | 4
NeronetTrainer | Version 1 | Sprint 1 | 721490 | US1: As a user, I want a basic user guide that would cover the installation of Neronet and its use via CLI . | Done | Joona Marjakangas |  |  | 3 | 6 | [7 empty] | 1 | discussed and reviewed Joona's work | Samuel Marisa | 2015-11-25 19:36 |  |  | Yes | 0 | 36 | 11
NeronetTrainer | Version 1 | Sprint 1 | 721490 | US1: As a user, I want a basic user guide that would cover the installation of Neronet and its use via CLI . | Done | Joona Marjakangas |  |  | 3 | 6 |  |  | 530790 | Adding Introduction and the list of contents and proofreading CLI | Done | Joona Marjakangas |  | 1 | Proofreading on CLI complete and the table of contents and introduction added | Joona Marjakangas | 2015-11-27 13:56 | 0 | 2 | Yes | 0 | 36 | 11
NeronetTrainer | Version 1 | Sprint 1 | 721490 | US1: As a user, I want a basic user guide that would cover the installation of Neronet and its use via CLI . | Done | Joona Marjakangas |  |  | 3 | 6 |  |  | 530790 | Adding Introduction and the list of contents and proofreading CLI | Done | Joona Marjakangas |  | 1 | Proofreading complete until deleting experiments | Joona Marjakangas | 2015-11-27 05:00 | 0 | 2 | Yes | 0 | 36 | 11
NeronetTrainer | Version 1 | Sprint 1 | 721490 | US1: As a user, I want a basic user guide that would cover the installation of Neronet and its use via CLI . | Done | Joona Marjakangas |  |  | 3 | 6 |  |  | 527103 | Implement CLI user guide | Done | Joona Marjakangas |  | 1.5 | Updated according to info from PO | Joona Marjakangas | 2015-12-02 13:29 | 0 | 10 | Yes | 0 | 36 | 11
NeronetTrainer | Version 1 | Sprint 1 | 721490 | US1: As a user, I want a basic user guide that would cover the installation of Neronet and its use via CLI . | Done | Joona Marjakangas |  |  | 3 | 6 |  |  | 527103 | Implement CLI user guide | Done | Joona Marjakangas |  | 1 | Fixed some syntax errors | Joona Marjakangas | 2015-11-26 21:45 | 0 | 10 | Yes | 0 | 36 | 11
NeronetTrainer | Version 1 | Sprint 1 | 721490 | US1: As a user, I want a basic user guide that would cover the installation of Neronet and its use via CLI . | Done | Joona Marjakangas |  |  | 3 | 6 |  |  | 527103 | Implement CLI user guide | Done | Joona Marjakangas |  | 5.5 | CLI user guide almost done except for proofreading and fixing some syntax errors | Joona Marjakangas | 2015-11-25 20:30 | 0 | 10 | Yes | 0 | 36 | 11
NeronetTrainer | Version 1 | Sprint 1 | 721490 | US1: As a user, I want a basic user guide that would cover the installation of Neronet and its use via CLI . | Done | Joona Marjakangas |  |  | 3 | 6 |  |  | 527103 | Implement CLI user guide | Done | Joona Marjakangas |  | 2.5 | Implementing user guide | Joona Marjakangas | 2015-11-20 20:53 | 0 | 10 | Yes | 0 | 36 | 11
NeronetTrainer | Version 1 | Sprint 1 | 721490 | US1: As a user, I want a basic user guide that would cover the installation of Neronet and its use via CLI . | Done | Joona Marjakangas |  |  | 3 | 6 |  |  | 525372 | Plan structure | Done | Joona Marjakangas |  | 2 | Planning structure | Joona Marjakangas | 2015-11-18 20:55 | 0 | 2 | Yes | 0 | 36 | 11
NeronetTrainer | Version 1 | Sprint 1 | 721490 | US1: As a user, I want a basic user guide that would cover the installation of Neronet and its use via CLI . | Done | Joona Marjakangas |  |  | 3 | 6 |  |  | 525372 | Plan structure | Done | Joona Marjakangas |  | 1 | Planning structure | Joona Marjakangas | 2015-11-20 19:00 | 0 | 2 | Yes | 0 | 36 | 11
NeronetTrainer | Version 1 | Sprint 1 | 721490 | US1: As a user, I want a basic user guide that would cover the installation of Neronet and its use via CLI . | Done | Joona Marjakangas |  |  | 3 | 6 |  |  | 525372 | Plan structure | Done | Joona Marjakangas |  | 1 | Skype with PO | Joona Marjakangas | 2015-11-20 20:00 | 0 | 2 | Yes | 0 | 36 | 11
NeronetTrainer | Version 1 | Sprint 1 | 721455 | US2: As a user, I want to specify clusters by address and type to specify my computing resources. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 1 | 3 |  |  | 529979 | Development | Done | Iiro Tähkä, Teemu Blomqvist |  | 2 |  | Teemu Blomqvist | 2015-11-25 20:02 | 0 | 2 | Yes | 1 | 38 | 12.11 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721455 | US2: As a user, I want to specify clusters by address and type to specify my computing resources. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 1 | 3 |  |  | 529979 | Development | Done | Iiro Tähkä, Teemu Blomqvist |  | 2 |  | Iiro Tähkä | 2015-11-25 20:02 | 0 | 2 | Yes | 1 | 38 | 12.11 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721455 | US2: As a user, I want to specify clusters by address and type to specify my computing resources. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 1 | 3 |  |  | 529978 | Planning | Done | Iiro Tähkä, Teemu Blomqvist |  | 0.3 |  | Iiro Tähkä | 2015-11-25 20:00 | 0 | 0.5 | Yes | 1 | 38 | 12.11 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721455 | US2: As a user, I want to specify clusters by address and type to specify my computing resources. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 1 | 3 |  |  | 529978 | Planning | Done | Iiro Tähkä, Teemu Blomqvist |  | 0.3 |  | Teemu Blomqvist | 2015-11-25 20:00 | 0 | 0.5 | Yes | 1 | 38 | 12.11 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721455 | US2: As a user, I want to specify clusters by address and type to specify my computing resources. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 1 | 3 |  |  | 529980 | Testing | Done | Iiro Tähkä, Teemu Blomqvist |  | 1 |  | Iiro Tähkä | 2015-11-25 20:03 | 0 | 0.5 | Yes | 1 | 38 | 12.11 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721455 | US2: As a user, I want to specify clusters by address and type to specify my computing resources. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 1 | 3 |  |  | 529980 | Testing | Done | Iiro Tähkä, Teemu Blomqvist |  | 1 |  | Teemu Blomqvist | 2015-11-25 20:03 | 0 | 0.5 | Yes | 1 | 38 | 12.11 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717298 | US3: As a user, I want to specify experiments by name, files and parameters. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 525382 | Development (Neroman) | Done | Iiro Tähkä, Teemu Blomqvist |  | 1 | Improvements on error handling | Teemu Blomqvist | 2015-11-20 21:04 | 0 | 2.5 | Yes | 2 | 39 | 12.12 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717298 | US3: As a user, I want to specify experiments by name, files and parameters. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 525382 | Development (Neroman) | Done | Iiro Tähkä, Teemu Blomqvist |  | 1 | Improvements on error handling | Iiro Tähkä | 2015-11-20 21:04 | 0 | 2.5 | Yes | 2 | 39 | 12.12 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717298 | US3: As a user, I want to specify experiments by name, files and parameters. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 525382 | Development (Neroman) | Done | Iiro Tähkä, Teemu Blomqvist |  | 2 | Basic bare bones implementation | Iiro Tähkä | 2015-11-18 19:26 | 0 | 2.5 | Yes | 2 | 39 | 12.12 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717298 | US3: As a user, I want to specify experiments by name, files and parameters. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 525382 | Development (Neroman) | Done | Iiro Tähkä, Teemu Blomqvist |  | 1 | Functions now raise exceptions | Teemu Blomqvist | 2015-11-25 16:43 | 0 | 2.5 | Yes | 2 | 39 | 12.12 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717298 | US3: As a user, I want to specify experiments by name, files and parameters. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 525382 | Development (Neroman) | Done | Iiro Tähkä, Teemu Blomqvist |  | 1 | Functions now raise exceptions | Iiro Tähkä | 2015-11-25 16:43 | 0 | 2.5 | Yes | 2 | 39 | 12.12 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717298 | US3: As a user, I want to specify experiments by name, files and parameters. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 525382 | Development (Neroman) | Done | Iiro Tähkä, Teemu Blomqvist |  | 2 | Basic bare bones implementation | Teemu Blomqvist | 2015-11-18 19:26 | 0 | 2.5 | Yes | 2 | 39 | 12.12 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717298 | US3: As a user, I want to specify experiments by name, files and parameters. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 525384 | Documentation | Done | Iiro Tähkä, Teemu Blomqvist |  | 0.5 | Added docstrings | Teemu Blomqvist | 2015-11-20 21:02 | 0 | 1 | Yes | 2 | 39 | 12.12 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717298 | US3: As a user, I want to specify experiments by name, files and parameters. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 525384 | Documentation | Done | Iiro Tähkä, Teemu Blomqvist |  | 0.5 | Added docstrings | Iiro Tähkä | 2015-11-20 21:02 | 0 | 1 | Yes | 2 | 39 | 12.12 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717298 | US3: As a user, I want to specify experiments by name, files and parameters. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 525381 | Planning | Done | Iiro Tähkä, Teemu Blomqvist |  | 0.2 | Planning related to database and code organization | Teemu Blomqvist | 2015-11-20 21:00 | 0 | 1.8 | Yes | 2 | 39 | 12.12 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717298 | US3: As a user, I want to specify experiments by name, files and parameters. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 525381 | Planning | Done | Iiro Tähkä, Teemu Blomqvist |  | 1.8 |  | Iiro Tähkä | 2015-11-18 17:35 | 0 | 1.8 | Yes | 2 | 39 | 12.12 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717298 | US3: As a user, I want to specify experiments by name, files and parameters. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 525381 | Planning | Done | Iiro Tähkä, Teemu Blomqvist |  | 1.8 |  | Teemu Blomqvist | 2015-11-18 17:35 | 0 | 1.8 | Yes | 2 | 39 | 12.12 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717298 | US3: As a user, I want to specify experiments by name, files and parameters. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 525381 | Planning | Done | Iiro Tähkä, Teemu Blomqvist |  | 0.2 | Planning related to database and code organization | Iiro Tähkä | 2015-11-20 21:00 | 0 | 1.8 | Yes | 2 | 39 | 12.12 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717298 | US3: As a user, I want to specify experiments by name, files and parameters. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 525383 | Testing | Done | Iiro Tähkä, Teemu Blomqvist |  | 2 | Studying and doing some unittests | Teemu Blomqvist | 2015-11-20 21:01 | 0 | 1 | Yes | 2 | 39 | 12.12 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717298 | US3: As a user, I want to specify experiments by name, files and parameters. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 525383 | Testing | Done | Iiro Tähkä, Teemu Blomqvist |  | 1 | Unittests for specifying experiments | Iiro Tähkä | 2015-11-25 16:44 | 0 | 1 | Yes | 2 | 39 | 12.12 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717298 | US3: As a user, I want to specify experiments by name, files and parameters. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 525383 | Testing | Done | Iiro Tähkä, Teemu Blomqvist |  | 2 | Studying and doing some unittests | Iiro Tähkä | 2015-11-20 21:01 | 0 | 1 | Yes | 2 | 39 | 12.12 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717298 | US3: As a user, I want to specify experiments by name, files and parameters. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 525383 | Testing | Done | Iiro Tähkä, Teemu Blomqvist |  | 1 | Unittests for specifying experiments | Teemu Blomqvist | 2015-11-25 16:44 | 0 | 1 | Yes | 2 | 39 | 12.12 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721468 | US4: As a user, I want to submit individual experiments to unmanaged nodes. | Done | Matias Pitkänen, Tuomo Perä |  |  | 5 | 6 | [7 empty] | 4.5 | made one to many sockets to work | Tuomo Perä | 2015-11-20 19:57 |  |  | Yes | 3 | 37 | 12.13 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721468 | US4: As a user, I want to submit individual experiments to unmanaged nodes. | Done | Matias Pitkänen, Tuomo Perä |  |  | 5 | 6 | [7 empty] | 2.3 | work on daemons and TCP servers | Samuel Marisa | 2015-11-27 17:23 |  |  | Yes | 3 | 37 | 12.13 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721468 | US4: As a user, I want to submit individual experiments to unmanaged nodes. | Done | Matias Pitkänen, Tuomo Perä |  |  | 5 | 6 | [7 empty] | 6 | refactored nerokid and neromum | Tuomo Perä | 2015-11-18 19:55 |  |  | Yes | 3 | 37 | 12.13 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721468 | US4: As a user, I want to submit individual experiments to unmanaged nodes. | Done | Matias Pitkänen, Tuomo Perä |  |  | 5 | 6 | [7 empty] | 6 |  | Matias Pitkänen | 2015-11-18 19:50 |  |  | Yes | 3 | 37 | 12.13 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721468 | US4: As a user, I want to submit individual experiments to unmanaged nodes. | Done | Matias Pitkänen, Tuomo Perä |  |  | 5 | 6 | [7 empty] | 4.5 |  | Matias Pitkänen | 2015-11-20 19:56 |  |  | Yes | 3 | 37 | 12.13 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721468 | US4: As a user, I want to submit individual experiments to unmanaged nodes. | Done | Matias Pitkänen, Tuomo Perä |  |  | 5 | 6 | [7 empty] | 0.7 | work on daemons | Samuel Marisa | 2015-11-25 20:39 |  |  | Yes | 3 | 37 | 12.13 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721468 | US4: As a user, I want to submit individual experiments to unmanaged nodes. | Done | Matias Pitkänen, Tuomo Perä |  |  | 5 | 6 | [7 empty] | 2.8 | consulting Tuomo and Matias on the development | Samuel Marisa | 2015-12-02 16:50 |  |  | Yes | 3 | 37 | 12.13 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721468 | US4: As a user, I want to submit individual experiments to unmanaged nodes. | Done | Matias Pitkänen, Tuomo Perä |  |  | 5 | 6 | [7 empty] | 5.5 | finalizing the work | Tuomo Perä | 2015-12-03 20:00 |  |  | Yes | 3 | 37 | 12.13 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721468 | US4: As a user, I want to submit individual experiments to unmanaged nodes. | Done | Matias Pitkänen, Tuomo Perä |  |  | 5 | 6 |  |  | 530012 | Create tests | Done | Matias Pitkänen, Tuomo Perä |  | 3 |  | Matias Pitkänen | 2015-11-27 19:40 | 0 | 3 | Yes | 3 | 37 | 12.13 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721468 | US4: As a user, I want to submit individual experiments to unmanaged nodes. | Done | Matias Pitkänen, Tuomo Perä |  |  | 5 | 6 |  |  | 530012 | Create tests | Done | Matias Pitkänen, Tuomo Perä |  | 3 |  | Tuomo Perä | 2015-11-27 19:40 | 0 | 3 | Yes | 3 | 37 | 12.13 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721468 | US4: As a user, I want to submit individual experiments to unmanaged nodes. | Done | Matias Pitkänen, Tuomo Perä |  |  | 5 | 6 |  |  | 530012 | Create tests | Done | Matias Pitkänen, Tuomo Perä |  | 8 |  | Tuomo Perä | 2015-12-02 21:51 | 0 | 3 | Yes | 3 | 37 | 12.13 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721468 | US4: As a user, I want to submit individual experiments to unmanaged nodes. | Done | Matias Pitkänen, Tuomo Perä |  |  | 5 | 6 |  |  | 530012 | Create tests | Done | Matias Pitkänen, Tuomo Perä |  | 8 |  | Matias Pitkänen | 2015-12-02 21:51 | 0 | 3 | Yes | 3 | 37 | 12.13 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721468 | US4: As a user, I want to submit individual experiments to unmanaged nodes. | Done | Matias Pitkänen, Tuomo Perä |  |  | 5 | 6 |  |  | 530015 | Documentation | Done | Matias Pitkänen, Tuomo Perä |  | 2 |  | Matias Pitkänen | 2015-11-27 19:40 | 0 | 2 | Yes | 3 | 37 | 12.13 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721468 | US4: As a user, I want to submit individual experiments to unmanaged nodes. | Done | Matias Pitkänen, Tuomo Perä |  |  | 5 | 6 |  |  | 530015 | Documentation | Done | Matias Pitkänen, Tuomo Perä |  | 2 |  | Tuomo Perä | 2015-11-27 19:40 | 0 | 2 | Yes | 3 | 37 | 12.13 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721468 | US4: As a user, I want to submit individual experiments to unmanaged nodes. | Done | Matias Pitkänen, Tuomo Perä |  |  | 5 | 6 |  |  | 529850 | Neroman can open a neromum using ssh | Done | Matias Pitkänen, Tuomo Perä |  | 5.5 |  | Tuomo Perä | 2015-11-25 19:36 | 0 | 5 | Yes | 3 | 37 | 12.13 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721468 | US4: As a user, I want to submit individual experiments to unmanaged nodes. | Done | Matias Pitkänen, Tuomo Perä |  |  | 5 | 6 |  |  | 529851 | Neroman can send files to nerokid to be run | Done | Matias Pitkänen, Tuomo Perä |  | 2 |  | Samuel Marisa | 2015-11-25 19:41 | 0 | 5 | Yes | 3 | 37 | 12.13 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721468 | US4: As a user, I want to submit individual experiments to unmanaged nodes. | Done | Matias Pitkänen, Tuomo Perä |  |  | 5 | 6 |  |  | 529851 | Neroman can send files to nerokid to be run | Done | Matias Pitkänen, Tuomo Perä |  | 5 |  | Matias Pitkänen | 2015-11-25 19:35 | 0 | 5 | Yes | 3 | 37 | 12.13 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721468 | US4: As a user, I want to submit individual experiments to unmanaged nodes. | Done | Matias Pitkänen, Tuomo Perä |  |  | 5 | 6 |  |  | 529849 | Neromum can open a nerokid using sockets | Done | Matias Pitkänen, Tuomo Perä |  | 1.5 | work with Tuomo | Samuel Marisa | 2015-11-25 19:42 | 0 | 5 | Yes | 3 | 37 | 12.13 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717303 | US5: As a user, I want an experiment status report so that I can review experiment status details. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 530902 | Development | Done | Iiro Tähkä, Teemu Blomqvist |  | 3 |  | Teemu Blomqvist | 2015-11-27 19:48 | 0 | 2 | Yes | 4 | 41 | 12.17 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717303 | US5: As a user, I want an experiment status report so that I can review experiment status details. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 530902 | Development | Done | Iiro Tähkä, Teemu Blomqvist |  | 6 |  | Teemu Blomqvist | 2015-12-02 17:48 | 0 | 2 | Yes | 4 | 41 | 12.17 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717303 | US5: As a user, I want an experiment status report so that I can review experiment status details. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 530902 | Development | Done | Iiro Tähkä, Teemu Blomqvist |  | 5 | Polishing status report and random help with integration | Iiro Tähkä | 2015-12-02 17:00 | 0 | 2 | Yes | 4 | 41 | 12.17 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717303 | US5: As a user, I want an experiment status report so that I can review experiment status details. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 530902 | Development | Done | Iiro Tähkä, Teemu Blomqvist |  | 3 |  | Iiro Tähkä | 2015-11-27 19:48 | 0 | 2 | Yes | 4 | 41 | 12.17 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717303 | US5: As a user, I want an experiment status report so that I can review experiment status details. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 530901 | Planning | Done | Iiro Tähkä, Teemu Blomqvist |  | 0.5 |  | Iiro Tähkä | 2015-11-27 19:47 | 0 | 0.5 | Yes | 4 | 41 | 12.17 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717303 | US5: As a user, I want an experiment status report so that I can review experiment status details. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 530901 | Planning | Done | Iiro Tähkä, Teemu Blomqvist |  | 0.5 |  | Teemu Blomqvist | 2015-11-27 19:47 | 0 | 0.5 | Yes | 4 | 41 | 12.17 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717303 | US5: As a user, I want an experiment status report so that I can review experiment status details. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 530904 | Testing | Done | Iiro Tähkä, Teemu Blomqvist |  | 1.5 |  | Teemu Blomqvist | 2015-11-27 19:49 | 0 | 1.5 | Yes | 4 | 41 | 12.17 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717303 | US5: As a user, I want an experiment status report so that I can review experiment status details. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 530904 | Testing | Done | Iiro Tähkä, Teemu Blomqvist |  | 1.5 |  | Iiro Tähkä | 2015-11-27 19:49 | 0 | 1.5 | Yes | 4 | 41 | 12.17 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534528 | Full review of the previous increment | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.5 |  | Iiro Tähkä | 2015-12-28 20:03 | 0 | 12
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534528 | Full review of the previous increment | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.5 |  | Teemu Blomqvist | 2015-12-28 20:08 | 0 | 12
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534528 | Full review of the previous increment | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.75 | Reviewing the code with the team | Samuel Marisa | 2015-12-28 20:04 | 0 | 12
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534528 | Full review of the previous increment | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.4 |  | Tuomo Perä | 2015-12-28 20:04 | 0 | 12
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534528 | Full review of the previous increment | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.5 |  | Matias Pitkänen | 2015-12-28 20:08 | 0 | 12
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534528 | Full review of the previous increment | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.5 | Reviewing the code with the team | Joona Marjakangas | 2015-12-28 16:50 | 0 | 12
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534582 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.5 | Samuel showed us his daemons | Iiro Tähkä | 2016-01-10 17:45 | 0 | 20
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534582 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | Daemons | Teemu Blomqvist | 2016-01-10 20:42 | 0 | 20
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534582 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.5 | scheduling the spring | Samuel Marisa | 2015-12-21 13:00 | 0 | 20
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534582 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.5 | discussed our work | Samuel Marisa | 2015-12-28 20:06 | 0 | 20
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534582 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | refactoring notes and backlog, notifying team on actualities. | Samuel Marisa | 2015-12-05 22:37 | 0 | 20
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534582 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | discussion | Teemu Blomqvist | 2016-01-08 15:13 | 0 | 20
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534590 | Setup readthedocs documentation | Done | Samuel Marisa, Tuomo Perä |  | 3 | Making it work | Teemu Blomqvist | 2016-01-08 17:08 | 0 | 3
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534581 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.4333 | held the sprit planning session | Joona Marjakangas | 2015-12-04 19:41 | 0 | 13
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534581 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.4333 | held the sprit planning session | Tuomo Perä | 2015-12-04 19:41 | 0 | 13
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534581 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.4333 | held the sprit planning session | Pyry Takala | 2015-12-04 19:41 | 0 | 13
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534581 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.4333 | held the sprit planning session | Teemu Blomqvist | 2015-12-04 19:41 | 0 | 13
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534581 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.4333 | held the sprit planning session | Matias Pitkänen | 2015-12-04 19:41 | 0 | 13
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534581 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.4333 | held the sprit planning session | Iiro Tähkä | 2015-12-04 19:41 | 0 | 13
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534581 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.4333 | held the sprit planning session | Samuel Marisa | 2015-12-04 19:41 | 0 | 13
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534583 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | Retro + Eero Lecture | Tuomo Perä | 2016-01-15 18:48 | 0 | 6
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534583 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | Retro + Eero Lecture | Eero Laukkanen | 2016-01-15 18:48 | 0 | 6
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534583 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | Retro + Eero Lecture | Samuel Marisa | 2016-01-15 18:48 | 0 | 6
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534583 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | Retro + Eero Lecture | Joona Marjakangas | 2016-01-15 18:48 | 0 | 6
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534583 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | Retro + Eero Lecture | Teemu Blomqvist | 2016-01-15 18:48 | 0 | 6
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534583 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | Retro + Eero Lecture | Iiro Tähkä | 2016-01-15 18:48 | 0 | 6
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534583 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | Retro + Eero Lecture | Matias Pitkänen | 2016-01-15 18:48 | 0 | 6
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534580 | Sprint review | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.5 |  | Matias Pitkänen | 2016-01-13 21:18 | 0 | 12
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534580 | Sprint review | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.5 |  | Samuel Marisa | 2016-01-13 21:18 | 0 | 12
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534580 | Sprint review | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.5 |  | Iiro Tähkä | 2016-01-13 21:18 | 0 | 12
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534580 | Sprint review | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.5 |  | Joona Marjakangas | 2016-01-13 21:18 | 0 | 12
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534580 | Sprint review | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.5 |  | Teemu Blomqvist | 2016-01-13 21:18 | 0 | 12
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534580 | Sprint review | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.5 |  | Tuomo Perä | 2016-01-13 21:18 | 0 | 12
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 550510 | System testing and debugging | Done | Joona Marjakangas |  | 4 | System testing | Joona Marjakangas | 2016-01-08 20:00 | 0 | 18
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 550510 | System testing and debugging | Done | Joona Marjakangas |  | 5.5 | System testing | Joona Marjakangas | 2016-01-06 20:30 | 0 | 18
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 550510 | System testing and debugging | Done | Joona Marjakangas |  | 6 | System testing | Joona Marjakangas | 2016-01-13 21:00 | 0 | 18
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534531 | Work toward an asynchronous daemon system | Done | Samuel Marisa, Tuomo Perä |  | 6 | reached a pretty good state for further development | Samuel Marisa | 2016-01-13 19:52 | 0 | 16
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534531 | Work toward an asynchronous daemon system | Done | Samuel Marisa, Tuomo Perä |  | 5 | worked on the daemon framework | Samuel Marisa | 2016-01-08 18:54 | 0 | 16
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534531 | Work toward an asynchronous daemon system | Done | Samuel Marisa, Tuomo Perä |  | 1 |  | Tuomo Perä | 2015-12-28 20:13 | 0 | 16
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534531 | Work toward an asynchronous daemon system | Done | Samuel Marisa, Tuomo Perä |  | 5 |  | Matias Pitkänen | 2016-01-10 18:58 | 0 | 16
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534531 | Work toward an asynchronous daemon system | Done | Samuel Marisa, Tuomo Perä |  | 5 | did a structural architecture diagram | Samuel Marisa | 2015-12-17 20:38 | 0 | 16
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534531 | Work toward an asynchronous daemon system | Done | Samuel Marisa, Tuomo Perä |  | 4 | worked on the daemon framework | Samuel Marisa | 2016-01-06 17:10 | 0 | 16
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534531 | Work toward an asynchronous daemon system | Done | Samuel Marisa, Tuomo Perä |  | 4 | Helping with the daemon | Matias Pitkänen | 2016-01-13 19:55 | 0 | 16
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534531 | Work toward an asynchronous daemon system | Done | Samuel Marisa, Tuomo Perä |  | 3 | worked on daemon | Tuomo Perä | 2016-01-06 22:04 | 0 | 16
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534531 | Work toward an asynchronous daemon system | Done | Samuel Marisa, Tuomo Perä |  | 4 | worked on the daemon framework | Samuel Marisa | 2015-12-28 20:05 | 0 | 16
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534531 | Work toward an asynchronous daemon system | Done | Samuel Marisa, Tuomo Perä |  | 9.5 | achieved pretty good kid-mum communication | Samuel Marisa | 2016-01-10 21:31 | 0 | 16
NeronetTrainer | Version 1 | Sprint 2 | 732143 | US10, As a user, I want the program enable easy setup | Done | Matias Pitkänen, Teemu Blomqvist |  |  | 4 | 6 | [7 empty] | 1.0167 | Going through the flow of installing and running experiments | Matias Pitkänen | 2016-01-08 18:03 |  |  | Yes | 4 | 32 | 12.7 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732143 | US10, As a user, I want the program enable easy setup | Done | Matias Pitkänen, Teemu Blomqvist |  |  | 4 | 6 | [7 empty] | 4.5 | Reading up on Python packaging | Matias Pitkänen | 2015-12-28 20:04 |  |  | Yes | 4 | 32 | 12.7 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732143 | US10, As a user, I want the program enable easy setup | Done | Matias Pitkänen, Teemu Blomqvist |  |  | 4 | 6 | [7 empty] | 4 | Setting up Python packaging | Teemu Blomqvist | 2016-01-06 18:05 |  |  | Yes | 4 | 32 | 12.7 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732143 | US10, As a user, I want the program enable easy setup | Done | Matias Pitkänen, Teemu Blomqvist |  |  | 4 | 6 | [7 empty] | 3 | Making neronet into a pip package | Matias Pitkänen | 2016-01-08 17:01 |  |  | Yes | 4 | 32 | 12.7 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732143 | US10, As a user, I want the program enable easy setup | Done | Matias Pitkänen, Teemu Blomqvist |  |  | 4 | 6 | [7 empty] | 4 | Setting up Python packaging | Matias Pitkänen | 2016-01-06 18:04 |  |  | Yes | 4 | 32 | 12.7 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732143 | US10, As a user, I want the program enable easy setup | Done | Matias Pitkänen, Teemu Blomqvist |  |  | 4 | 6 | [7 empty] | 1.5 | Reading up on Python packaging | Teemu Blomqvist | 2015-12-28 20:04 |  |  | Yes | 4 | 32 | 12.7 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732143 | US10, As a user, I want the program enable easy setup | Done | Matias Pitkänen, Teemu Blomqvist |  |  | 4 | 6 | [7 empty] | 3 | Making neronet into a pip package | Teemu Blomqvist | 2016-01-08 17:01 |  |  | Yes | 4 | 32 | 12.7 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732143 | US10, As a user, I want the program enable easy setup | Done | Matias Pitkänen, Teemu Blomqvist |  |  | 4 | 6 | [7 empty] | 4.5 |  | Teemu Blomqvist | 2016-01-13 20:51 |  |  | Yes | 4 | 32 | 12.7 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732142 | US6, As a user, I want to set my preferences (name, email, default cluster) | Done | Joona Marjakangas |  |  | 2 | 5 |  |  | 543621 | Implementing | Done | Joona Marjakangas |  | 1.0333 | Implementing | Joona Marjakangas | 2015-12-28 19:03 | 0 | 5 | Yes | 1 | 33 | 12.8 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732142 | US6, As a user, I want to set my preferences (name, email, default cluster) | Done | Joona Marjakangas |  |  | 2 | 5 |  |  | 543619 | Peer review | Done | Matias Pitkänen |  | 2 |  | Matias Pitkänen | 2016-01-13 19:53 | 0 | 1 | Yes | 1 | 33 | 12.8 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732142 | US6, As a user, I want to set my preferences (name, email, default cluster) | Done | Joona Marjakangas |  |  | 2 | 5 |  |  | 543618 | Planning | Done | Joona Marjakangas |  | 1 | Reading the previous code and planning changes | Joona Marjakangas | 2015-12-28 18:01 | 0 | 0.5 | Yes | 1 | 33 | 12.8 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732142 | US6, As a user, I want to set my preferences (name, email, default cluster) | Done | Joona Marjakangas |  |  | 2 | 5 |  |  | 543620 | Testing | Done | Joona Marjakangas |  | 1 | System testing | Joona Marjakangas | 2016-01-08 16:00 | 0 | 1.5 | Yes | 1 | 33 | 12.8 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 734098 | US7, As a user, I want my experiment config attributes to support generation of value combinations | Done | Iiro Tähkä, Joona Marjakangas |  |  | 1 | 6 |  |  | 543614 | Implementing & Integrating | Done | Iiro Tähkä, Joona Marjakangas |  | 0.5 | Documentation | Iiro Tähkä | 2016-01-09 18:08 | 0 | 5 | Yes | 2 | 25 | 12.0 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 734098 | US7, As a user, I want my experiment config attributes to support generation of value combinations | Done | Iiro Tähkä, Joona Marjakangas |  |  | 1 | 6 |  |  | 543614 | Implementing & Integrating | Done | Iiro Tähkä, Joona Marjakangas |  | 1 | Implemented a function to create the combinations | Iiro Tähkä | 2016-01-07 16:42 | 0 | 5 | Yes | 2 | 25 | 12.0 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 734098 | US7, As a user, I want my experiment config attributes to support generation of value combinations | Done | Iiro Tähkä, Joona Marjakangas |  |  | 1 | 6 |  |  | 543614 | Implementing & Integrating | Done | Iiro Tähkä, Joona Marjakangas |  | 2 | Made a functional working version | Iiro Tähkä | 2016-01-09 16:49 | 0 | 5 | Yes | 2 | 25 | 12.0 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 734098 | US7, As a user, I want my experiment config attributes to support generation of value combinations | Done | Iiro Tähkä, Joona Marjakangas |  |  | 1 | 6 |  |  | 543614 | Implementing & Integrating | Done | Iiro Tähkä, Joona Marjakangas |  | 1 | Integration | Iiro Tähkä | 2016-01-13 20:48 | 0 | 5 | Yes | 2 | 25 | 12.0 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 734098 | US7, As a user, I want my experiment config attributes to support generation of value combinations | Done | Iiro Tähkä, Joona Marjakangas |  |  | 1 | 6 |  |  | 543611 | Peer review | Done |  |  | 0.5 |  | Teemu Blomqvist | 2016-01-13 20:50 | 0 | 1 | Yes | 2 | 25 | 12.0 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 734098 | US7, As a user, I want my experiment config attributes to support generation of value combinations | Done | Iiro Tähkä, Joona Marjakangas |  |  | 1 | 6 |  |  | 543613 | Planning | Done | Iiro Tähkä, Joona Marjakangas |  | 1 |  | Iiro Tähkä | 2016-01-06 15:00 | 0 | 1 | Yes | 2 | 25 | 12.0 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 734098 | US7, As a user, I want my experiment config attributes to support generation of value combinations | Done | Iiro Tähkä, Joona Marjakangas |  |  | 1 | 6 |  |  | 543612 | Testing | Done | Iiro Tähkä, Joona Marjakangas |  | 1 |  | Iiro Tähkä | 2016-01-10 16:17 | 0 | 1 | Yes | 2 | 25 | 12.0 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732144 | US8, As a user, I want my experiment specifications to be able to inherit properties | Done | Iiro Tähkä, Joona Marjakangas |  |  | 2 | 6 |  |  | 543617 | Implementing & Integrating | Done | Iiro Tähkä, Joona Marjakangas |  | 0.5 | Documentation | Iiro Tähkä | 2016-01-09 18:09 | 0 | 10 | Yes | 3 | 31 | 12.6 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732144 | US8, As a user, I want my experiment specifications to be able to inherit properties | Done | Iiro Tähkä, Joona Marjakangas |  |  | 2 | 6 |  |  | 543617 | Implementing & Integrating | Done | Iiro Tähkä, Joona Marjakangas |  | 3.5 | Refactoring config parsing and Inheritance | Iiro Tähkä | 2015-12-28 20:05 | 0 | 10 | Yes | 3 | 31 | 12.6 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732144 | US8, As a user, I want my experiment specifications to be able to inherit properties | Done | Iiro Tähkä, Joona Marjakangas |  |  | 2 | 6 |  |  | 543617 | Implementing & Integrating | Done | Iiro Tähkä, Joona Marjakangas |  | 2 | Impemented a class for experiments | Iiro Tähkä | 2016-01-10 19:45 | 0 | 10 | Yes | 3 | 31 | 12.6 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732144 | US8, As a user, I want my experiment specifications to be able to inherit properties | Done | Iiro Tähkä, Joona Marjakangas |  |  | 2 | 6 |  |  | 543617 | Implementing & Integrating | Done | Iiro Tähkä, Joona Marjakangas |  | 3 | Integration | Iiro Tähkä | 2016-01-13 20:47 | 0 | 10 | Yes | 3 | 31 | 12.6 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732144 | US8, As a user, I want my experiment specifications to be able to inherit properties | Done | Iiro Tähkä, Joona Marjakangas |  |  | 2 | 6 |  |  | 543610 | Peer review | Done |  |  | 1 | Reviewed mostly the code | Teemu Blomqvist | 2016-01-13 20:49 | 0 | 2 | Yes | 3 | 31 | 12.6 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732144 | US8, As a user, I want my experiment specifications to be able to inherit properties | Done | Iiro Tähkä, Joona Marjakangas |  |  | 2 | 6 |  |  | 543615 | Planning | Done | Iiro Tähkä, Joona Marjakangas |  | 1 |  | Iiro Tähkä | 2015-12-28 20:04 | 0 | 2 | Yes | 3 | 31 | 12.6 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732144 | US8, As a user, I want my experiment specifications to be able to inherit properties | Done | Iiro Tähkä, Joona Marjakangas |  |  | 2 | 6 |  |  | 543616 | Testing | Done | Iiro Tähkä, Joona Marjakangas |  | 2.5 |  | Iiro Tähkä | 2016-01-10 16:18 | 0 | 2 | Yes | 3 | 31 | 12.6 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 734099 | US9, As a user, I want to see a basic status report in the GUI | Done | Tuomo Perä |  |  | 3 | 4 | [7 empty] | 7.5 | finished qt mockup | Tuomo Perä | 2016-01-13 22:09 |  |  | Yes | 0 | 24 | 14.6 | As a user, I want an interactive GUI to utilize Neroman easily.
NeronetTrainer | Version 1 | Sprint 2 | 734099 | US9, As a user, I want to see a basic status report in the GUI | Done | Tuomo Perä |  |  | 3 | 4 | [7 empty] | 5 | problems with qt installing | Tuomo Perä | 2016-01-08 22:13 |  |  | Yes | 0 | 24 | 14.6 | As a user, I want an interactive GUI to utilize Neroman easily.
NeronetTrainer | Version 1 | Sprint 2 | 734099 | US9, As a user, I want to see a basic status report in the GUI | Done | Tuomo Perä |  |  | 3 | 4 | [7 empty] | 5 |  | Tuomo Perä | 2016-01-23 00:38 |  |  | Yes | 0 | 24 | 14.6 | As a user, I want an interactive GUI to utilize Neroman easily.
NeronetTrainer | Version 1 | Sprint 2 | 734099 | US9, As a user, I want to see a basic status report in the GUI | Done | Tuomo Perä |  |  | 3 | 4 | [7 empty] | 5 | Started with basic qt application | Tuomo Perä | 2016-01-06 22:27 |  |  | Yes | 0 | 24 | 14.6 | As a user, I want an interactive GUI to utilize Neroman easily.
NeronetTrainer | Version 1 | Sprint 2 | 734099 | US9, As a user, I want to see a basic status report in the GUI | Done | Tuomo Perä |  |  | 3 | 4 | [7 empty] | 4 | attended skype and reserached qt installing | Tuomo Perä | 2016-01-10 22:11 |  |  | Yes | 0 | 24 | 14.6 | As a user, I want an interactive GUI to utilize Neroman easily.
NeronetTrainer | Version 1 | Sprint 2 | 734099 | US9, As a user, I want to see a basic status report in the GUI | Done | Tuomo Perä |  |  | 3 | 4 | [7 empty] | 5 |  | Tuomo Perä | 2016-01-29 14:24 |  |  | Yes | 0 | 24 | 14.6 | As a user, I want an interactive GUI to utilize Neroman easily.
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 551555 | Comprehensive system testing | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | Tested the system during the weekend | Samuel Marisa | 2016-01-31 13:50 | 0 | 12
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 551555 | Comprehensive system testing | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | Made a simple_system_test.py | Teemu Blomqvist | 2016-01-20 19:18 | 0 | 12
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 560789 | EES | Done | Joona Marjakangas, Tuomo Perä |  | 2 | EES3 | Joona Marjakangas | 2016-01-27 17:00 | 0 | 4
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550756 | Explore the possibilities and limitations of Qt and web based GUI solutions | Done | Tuomo Perä |  | 6 | Creating a cluster view | Tuomo Perä | 2016-01-27 19:48 | 0 | 8
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550757 | Finish asychronous system update | Done | Iiro Tähkä, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist |  | 6 | Debugging the daemon | Matias Pitkänen | 2016-01-27 19:46 | 0 | 20
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550757 | Finish asychronous system update | Done | Iiro Tähkä, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist |  | 5 | Work on the daemon logic. | Samuel Marisa | 2016-01-27 19:48 | 0 | 20
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550757 | Finish asychronous system update | Done | Iiro Tähkä, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist |  | 2 | Refactoring the daemon logic. | Teemu Blomqvist | 2016-01-22 19:04 | 0 | 20
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550757 | Finish asychronous system update | Done | Iiro Tähkä, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist |  | 5 | Continuing on the daemon | Matias Pitkänen | 2016-01-29 19:05 | 0 | 20
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550757 | Finish asychronous system update | Done | Iiro Tähkä, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist |  | 6.5 | Helped with working on the daemon | Teemu Blomqvist | 2016-01-29 21:17 | 0 | 20
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550757 | Finish asychronous system update | Done | Iiro Tähkä, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist |  | 2 | Iiro and Samuel tweaked config_parser, Teemu revamped Daemon | Iiro Tähkä | 2016-01-15 18:51 | 0 | 20
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550757 | Finish asychronous system update | Done | Iiro Tähkä, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist |  | 2 | Refactoring the daemon logic. | Samuel Marisa | 2016-01-22 19:04 | 0 | 20
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550757 | Finish asychronous system update | Done | Iiro Tähkä, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist |  | 5 | Worked on daemon | Matias Pitkänen | 2016-01-22 18:43 | 0 | 20
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550757 | Finish asychronous system update | Done | Iiro Tähkä, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist |  | 7.5 | Finished and tested the essential deamon logic | Samuel Marisa | 2016-01-29 21:10 | 0 | 20
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550757 | Finish asychronous system update | Done | Iiro Tähkä, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist |  | 2 | Iiro and Samuel tweaked config_parser, Teemu revamped Daemon | Teemu Blomqvist | 2016-01-15 18:51 | 0 | 20
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550757 | Finish asychronous system update | Done | Iiro Tähkä, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist |  | 2 | Iiro and Samuel tweaked config_parser, Teemu revamped Daemon | Samuel Marisa | 2016-01-15 18:51 | 0 | 20
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550757 | Finish asychronous system update | Done | Iiro Tähkä, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist |  | 0.5 | Small fixes to daemon.py | Teemu Blomqvist | 2016-01-28 00:05 | 0 | 20
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550757 | Finish asychronous system update | Done | Iiro Tähkä, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist |  | 5.5 | Debugging the daemon | Teemu Blomqvist | 2016-01-27 19:48 | 0 | 20
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 551641 | General discussion | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 |  | Samuel Marisa | 2016-01-15 14:00 | 0 | 10
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 551641 | General discussion | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 |  | Joona Marjakangas | 2016-01-15 14:00 | 0 | 10
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 551641 | General discussion | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 |  | Tuomo Perä | 2016-01-15 18:48 | 0 | 10
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 551641 | General discussion | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.5 | scrum | Matias Pitkänen | 2016-01-20 17:07 | 0 | 10
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 551641 | General discussion | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.5 | Downtime | Tuomo Perä | 2016-01-20 14:30 | 0 | 10
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 551641 | General discussion | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 |  | Matias Pitkänen | 2016-01-15 18:48 | 0 | 10
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 551641 | General discussion | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.5 | scrum | Teemu Blomqvist | 2016-01-20 17:07 | 0 | 10
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 551641 | General discussion | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.5 | scrum | Iiro Tähkä | 2016-01-20 17:07 | 0 | 10
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 551641 | General discussion | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.5 | scrum | Joona Marjakangas | 2016-01-20 17:07 | 0 | 10
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 551641 | General discussion | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.5 | scrum | Tuomo Perä | 2016-01-20 17:07 | 0 | 10
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 551641 | General discussion | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 |  | Teemu Blomqvist | 2016-01-15 14:00 | 0 | 10
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 551641 | General discussion | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 |  | Teemu Blomqvist | 2016-01-22 19:05 | 0 | 10
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 560141 | Quick start guide | Done | Joona Marjakangas |  | 3 | Quick start guide finished | Joona Marjakangas | 2016-01-29 17:00 | 0 | 3
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 560141 | Quick start guide | Done | Joona Marjakangas |  | 0.5 | Added quick start guide to readthedocs | Teemu Blomqvist | 2016-02-03 18:21 | 0 | 3
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 553988 | Random Coding Related Tasks | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | Trying to get the sprint work | Tuomo Perä | 2016-01-20 17:08 | 0 | 0
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 553988 | Random Coding Related Tasks | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3.5 | Studied Daemon | Iiro Tähkä | 2016-01-27 16:39 | 0 | 0
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 553988 | Random Coding Related Tasks | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | Improve Experiment interface | Iiro Tähkä | 2016-01-14 17:12 | 0 | 0
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 553988 | Random Coding Related Tasks | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | Trying to get the sprint work | Teemu Blomqvist | 2016-01-20 17:08 | 0 | 0
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 553988 | Random Coding Related Tasks | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | Ensuring a working version of neronet is in PyPI | Teemu Blomqvist | 2016-01-30 13:00 | 0 | 0
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 553988 | Random Coding Related Tasks | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | Trying to get the sprint work | Iiro Tähkä | 2016-01-20 17:08 | 0 | 0
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 553988 | Random Coding Related Tasks | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | Improved some artifacts | Iiro Tähkä | 2016-01-29 20:31 | 0 | 0
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 553988 | Random Coding Related Tasks | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | Improved neroman and config parser interface | Iiro Tähkä | 2016-01-22 18:36 | 0 | 0
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550790 | Revert to Python2.7 (possibly support both) | Done | Joona Marjakangas, Matias Pitkänen, Tuomo Perä |  | 2 |  | Matias Pitkänen | 2016-01-15 18:46 | 0 | 10
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550790 | Revert to Python2.7 (possibly support both) | Done | Joona Marjakangas, Matias Pitkänen, Tuomo Perä |  | 2 | Refactoring deamon logic. | Teemu Blomqvist | 2016-01-22 19:03 | 0 | 10
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550790 | Revert to Python2.7 (possibly support both) | Done | Joona Marjakangas, Matias Pitkänen, Tuomo Perä |  | 2 |  | Tuomo Perä | 2016-01-15 18:46 | 0 | 10
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550790 | Revert to Python2.7 (possibly support both) | Done | Joona Marjakangas, Matias Pitkänen, Tuomo Perä |  | 2 | Refactoring deamon logic. | Samuel Marisa | 2016-01-22 19:03 | 0 | 10
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550794 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.5 |  | Pyry Takala | 2016-01-13 21:29 | 0 | 3
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550794 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.5 |  | Teemu Blomqvist | 2016-01-13 21:29 | 0 | 3
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550794 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.5 |  | Samuel Marisa | 2016-01-13 21:29 | 0 | 3
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550794 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.5 |  | Matias Pitkänen | 2016-01-13 21:29 | 0 | 3
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550794 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.5 |  | Joona Marjakangas | 2016-01-13 21:29 | 0 | 3
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550794 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.5 |  | Tuomo Perä | 2016-01-13 21:29 | 0 | 3
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550794 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.5 |  | Iiro Tähkä | 2016-01-13 21:29 | 0 | 3
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550791 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.5 |  | Matias Pitkänen | 2016-02-03 16:25 | 0 | 6
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550791 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.5 |  | Teemu Blomqvist | 2016-02-03 16:25 | 0 | 6
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550791 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.5 |  | Joona Marjakangas | 2016-02-03 16:25 | 0 | 6
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550791 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.5 |  | Iiro Tähkä | 2016-02-03 16:25 | 0 | 6
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550791 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.5 |  | Tuomo Perä | 2016-02-03 16:25 | 0 | 6
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550793 | Sprint review | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.2 | sprint review via Skype | Pyry Takala | 2016-02-01 17:10 | 0 | 7
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550793 | Sprint review | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.2 | sprint review via Skype | Teemu Blomqvist | 2016-02-01 17:10 | 0 | 7
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550793 | Sprint review | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | sprint planning via skype | Tuomo Perä | 2016-02-01 17:10 | 0 | 7
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550793 | Sprint review | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.2 | sprint review via Skype | Joona Marjakangas | 2016-02-01 17:10 | 0 | 7
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550793 | Sprint review | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.2 | sprint review via Skype | Matias Pitkänen | 2016-02-01 17:10 | 0 | 7
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550793 | Sprint review | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.2 | sprint review via skype | Samuel Marisa | 2016-02-01 17:10 | 0 | 7
NeronetTrainer | Version 1 | Sprint 3 | 732138 | US11, As a user, I want to save important information about my clusters | Done | Matias Pitkänen, Teemu Blomqvist |  |  | 1 | 4 | [7 empty] | 3 |  | Matias Pitkänen | 2016-01-20 19:10 |  |  | Yes | 0 | 35 | 12.10 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 3 | 732138 | US11, As a user, I want to save important information about my clusters | Done | Matias Pitkänen, Teemu Blomqvist |  |  | 1 | 4 | [7 empty] | 2.5 | Changing status report to display extra cluster information | Matias Pitkänen | 2016-01-20 17:07 |  |  | Yes | 0 | 35 | 12.10 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 3 | 732139 | US12, As a user, I want to group my clusters | Done | Joona Marjakangas |  |  | 1 | 4 |  |  | 560787 | Enabling user to submit to a group | Done | Joona Marjakangas |  | 1.9333 | User can now submit experiments using a group name instead of a cluster name. The actual cluster is chosen randomly | Joona Marjakangas | 2016-01-31 22:56 | 0 | 2 | Yes | 1 | 34 | 12.9 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 3 | 732146 | US13, As a user, I want to delete obsolete versions of my experiments | Done | Iiro Tähkä |  |  | 1 | 4 | [7 empty] | 0.5 | Simple delete functionality | Iiro Tähkä | 2016-01-20 17:33 |  |  | Yes | 2 | 29 | 12.4 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 3 | 732145 | US14, As a user, I want configurable criteria for experiment warnings and autotermination | Done | Joona Marjakangas |  |  | 4 | 4 | [7 empty] | 1 | Integrated experimentation warning/autotermination without functionality | Iiro Tähkä | 2016-01-29 20:32 |  |  | Yes | 3 | 30 | 12.5 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 3 | 732145 | US14, As a user, I want configurable criteria for experiment warnings and autotermination | Done | Joona Marjakangas |  |  | 4 | 4 |  |  | 560137 | Creating and testing ExperimentWarning class to work with nerokid | Done | Joona Marjakangas |  | 4 | Created and tested the class | Joona Marjakangas | 2016-01-27 20:00 | 0 | 4 | Yes | 3 | 30 | 12.5 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 3 | 732145 | US14, As a user, I want configurable criteria for experiment warnings and autotermination | Done | Joona Marjakangas |  |  | 4 | 4 |  |  | 560138 | Enabling nerokid to send warnings and autoterminate together with the ExperimentWarning class | Done | Joona Marjakangas |  | 5 | Nerokid send warnings to neromum from which neroman can update data. Nerokid can auoterminate itself | Joona Marjakangas | 2016-01-31 21:00 | 0 | 2 | Yes | 3 | 30 | 12.5 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 3 | 732145 | US14, As a user, I want configurable criteria for experiment warnings and autotermination | Done | Joona Marjakangas |  |  | 4 | 4 |  |  | 560139 | Enabling neroman to parse and send the required arguments to neromum and -kids | Done | Joona Marjakangas |  | 3 | Parsing arguments in config parser and saving them to Experiment object | Joona Marjakangas | 2016-01-29 20:00 | 0 | 3 | Yes | 3 | 30 | 12.5 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 3 | 717301 | US15, As a user, I want a status report so that I can get an overview. | Done | Iiro Tähkä |  |  | 1 | 5 |  | As a user, I want a collections status report so that I can get an overview of collections. | [5 empty] | 1.7 | Improved on status report and the interface for getting status reports | Iiro Tähkä | 2016-01-20 19:15 |  |  | Yes | 4 | 43 | 12.19 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 561226 | Finding and supporting test users, marketing etc. | Done | Joona Marjakangas, Samuel Marisa |  | 3 | Meeting Simo and preparing for it | Joona Marjakangas | 2016-02-24 17:00 | 0 | 20
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 561225 | General appearance, marketability and clarity improvement | Done | Joona Marjakangas |  | 3 | Making user experience better according to input from PO | Joona Marjakangas | 2016-02-18 19:00 | 0 | 8
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 567213 | General discussion and coordination, daily scrums | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.5 | discussed my commits and current todo | Samuel Marisa | 2016-02-10 19:11 | 0 | 10
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 561224 | Implement improvements based on user feedback | Done | Samuel Marisa |  | 2.2 | Improvements from Pyrys feedback. | Samuel Marisa | 2016-02-18 18:23 | 0 | 20
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 575007 | Progress report | Done | Joona Marjakangas, Tuomo Perä |  | 3.5 | Preparing progress report and artifacts | Joona Marjakangas | 2016-02-27 22:30 | 0 | 6
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 575007 | Progress report | Done | Joona Marjakangas, Tuomo Perä |  | 1.1 | Improvements and peer review | Teemu Blomqvist | 2016-02-29 00:30 | 0 | 6
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 575007 | Progress report | Done | Joona Marjakangas, Tuomo Perä |  | 1.1 | Improvements and peer review | Iiro Tähkä | 2016-02-29 00:30 | 0 | 6
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 575007 | Progress report | Done | Joona Marjakangas, Tuomo Perä |  | 4 | Preparing progress report and artifacts | Joona Marjakangas | 2016-02-26 18:00 | 0 | 6
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 575007 | Progress report | Done | Joona Marjakangas, Tuomo Perä |  | 1.1 | Improvements and peer review | Samuel Marisa | 2016-02-29 00:30 | 0 | 6
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 575966 | Random Coding Related Tasks | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.95 | Support for Pyry | Iiro Tähkä | 2016-02-26 19:10
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 575966 | Random Coding Related Tasks | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.5 | Testing to ensure a working version in PyPI. This was in Sprint 5 but moving this time addition is too difficult | Teemu Blomqvist | 2016-03-18 00:40
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 575966 | Random Coding Related Tasks | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 4 | Testing, improving documentation and manual, debugging, made sure termination works after somebody made changes to code base, etc. | Joona Marjakangas | 2016-03-23 07:26
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 575966 | Random Coding Related Tasks | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 6 |  | Teemu Blomqvist | 2016-02-10 18:23
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 575966 | Random Coding Related Tasks | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 4 | Tried to make argcomplete work (unsuccessfully) | Teemu Blomqvist | 2016-02-12 18:17
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 575966 | Random Coding Related Tasks | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | Studied dynamic imports | Iiro Tähkä | 2016-02-25 18:19
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 564112 | Setup automated tests and continuous integration | Done | Joona Marjakangas |  | 3 | Studying and preparing travis CI | Joona Marjakangas | 2016-02-10 17:00 | 0 | 6
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 564112 | Setup automated tests and continuous integration | Done | Joona Marjakangas |  | 2 | Setting up travis CI and updating unit tests | Joona Marjakangas | 2016-02-12 21:10 | 0 | 6
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 564112 | Setup automated tests and continuous integration | Done | Joona Marjakangas |  | 5 | Updating unit tests | Joona Marjakangas | 2016-02-28 19:00 | 0 | 6
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 561786 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | Sprint planning via Skype | Pyry Takala | 2016-02-01 17:10 | 0 | 7
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 561786 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | Sprint planning via Skype | Teemu Blomqvist | 2016-02-01 17:10 | 0 | 7
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 561786 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | Sprint planning via Skype | Samuel Marisa | 2016-02-01 17:10 | 0 | 7
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 561786 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | Planning with Matias & co | Samuel Marisa | 2016-02-05 16:00 | 0 | 7
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 561786 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | Sprint planning via Skype | Tuomo Perä | 2016-02-01 17:10 | 0 | 7
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 561786 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | Sprint planning via Skype | Joona Marjakangas | 2016-02-01 17:10 | 0 | 7
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 561786 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 | Sprint planning via Skype | Matias Pitkänen | 2016-02-01 17:10 | 0 | 7
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 564114 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 |  | Matias Pitkänen | 2016-02-26 17:45 | 0 | 6
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 564114 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 |  | Tuomo Perä | 2016-02-26 17:45 | 0 | 6
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 564114 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 |  | Teemu Blomqvist | 2016-02-26 17:45 | 0 | 6
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 564114 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 |  | Iiro Tähkä | 2016-02-26 17:45 | 0 | 6
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 564114 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1 |  | Joona Marjakangas | 2016-02-26 17:45 | 0 | 6
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 564117 | Sprint review | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.1 | Progress review 2 | Joona Marjakangas | 2016-02-29 15:00 | 0 | 7
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 564117 | Sprint review | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.1 | Progress review 2 | Tuomo Perä | 2016-02-29 15:00 | 0 | 7
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 564117 | Sprint review | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.1 | Progress review 2 | Eero Laukkanen | 2016-02-29 15:00 | 0 | 7
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 564117 | Sprint review | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.1 | Progress review 2 | Samuel Marisa | 2016-02-29 15:00 | 0 | 7
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 564117 | Sprint review | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.1 | Progress review 2 | Iiro Tähkä | 2016-02-29 15:00 | 0 | 7
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 564117 | Sprint review | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.1 | Progress review 2 | Matias Pitkänen | 2016-02-29 15:00 | 0 | 7
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 564117 | Sprint review | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.1 | Progress review 2 | Pyry Takala | 2016-02-29 15:00 | 0 | 7
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 575003 | Sprint review demo preparation | Done | Joona Marjakangas, Samuel Marisa |  | 0.5 | peer review | Samuel Marisa | 2016-02-28 22:00 | 0 | 12
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 575003 | Sprint review demo preparation | Done | Joona Marjakangas, Samuel Marisa |  | 2 |  | Samuel Marisa | 2016-02-24 19:30 | 0 | 12
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 575003 | Sprint review demo preparation | Done | Joona Marjakangas, Samuel Marisa |  | 1 | preparing the demo | Joona Marjakangas | 2016-02-29 14:00 | 0 | 12
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 575003 | Sprint review demo preparation | Done | Joona Marjakangas, Samuel Marisa |  | 1 | preparing for the meeting | Samuel Marisa | 2016-02-29 12:10 | 0 | 12
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 575003 | Sprint review demo preparation | Done | Joona Marjakangas, Samuel Marisa |  | 4 | preparing the demo | Matias Pitkänen | 2016-02-26 17:46 | 0 | 12
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 575003 | Sprint review demo preparation | Done | Joona Marjakangas, Samuel Marisa |  | 1 | preparing the demo | Samuel Marisa | 2016-02-29 14:00 | 0 | 12
NeronetTrainer | Version 1 | Sprint 4 | 717307 | US 21, As a user, I want to submit individual experiments to be run on Slurm clusters. | Deferred |  |  |  | 5 | 3 | [7 empty] | 3 | Initial exploration with Slurm. | Samuel Marisa | 2016-02-05 21:00 |  |  | Yes | 1 | 45 | 12.14 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 4 | 717307 | US 21, As a user, I want to submit individual experiments to be run on Slurm clusters. | Deferred |  |  |  | 5 | 3 | [7 empty] | 3 | working on slurmification | Samuel Marisa | 2016-02-10 19:09 |  |  | Yes | 1 | 45 | 12.14 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 4 | 717307 | US 21, As a user, I want to submit individual experiments to be run on Slurm clusters. | Deferred |  |  |  | 5 | 3 | [7 empty] | 4 | working on clean_experiment and defining sbatch | Matias Pitkänen | 2016-02-10 19:02 |  |  | Yes | 1 | 45 | 12.14 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 4 | 717307 | US 21, As a user, I want to submit individual experiments to be run on Slurm clusters. | Deferred |  |  |  | 5 | 3 | [7 empty] | 6 | fighting on internode socket communication for Slurm | Samuel Marisa | 2016-02-12 19:14 |  |  | Yes | 1 | 45 | 12.14 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 4 | 717307 | US 21, As a user, I want to submit individual experiments to be run on Slurm clusters. | Deferred |  |  |  | 5 | 3 | [7 empty] | 5 | Cluster logic and related refactoring and improvement. | Samuel Marisa | 2016-02-06 14:32 |  |  | Yes | 1 | 45 | 12.14 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 4 | 717307 | US 21, As a user, I want to submit individual experiments to be run on Slurm clusters. | Deferred |  |  |  | 5 | 3 | [7 empty] | 2 | Worked toward Slurm support | Samuel Marisa | 2016-02-18 20:23 |  |  | Yes | 1 | 45 | 12.14 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 4 | 717307 | US 21, As a user, I want to submit individual experiments to be run on Slurm clusters. | Deferred |  |  |  | 5 | 3 | [7 empty] | 2 | worked on sockets | Matias Pitkänen | 2016-02-12 19:15 |  |  | Yes | 1 | 45 | 12.14 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 4 | 764159 | US16, As a user, I want to have example use cases that I can study | Done | Teemu Blomqvist |  |  | 3 | 4 | [7 empty] | 0.3 | peer review | Teemu Blomqvist | 2016-02-28 22:10 |  |  | Yes | 0 | 18 | 10
NeronetTrainer | Version 1 | Sprint 4 | 764159 | US16, As a user, I want to have example use cases that I can study | Done | Teemu Blomqvist |  |  | 3 | 4 | [7 empty] | 1 | Making an example to user guide | Matias Pitkänen | 2016-02-10 19:02 |  |  | Yes | 0 | 18 | 10
NeronetTrainer | Version 1 | Sprint 4 | 764159 | US16, As a user, I want to have example use cases that I can study | Done | Teemu Blomqvist |  |  | 3 | 4 | [7 empty] | 0.3 | peer review | Joona Marjakangas | 2016-02-28 22:10 |  |  | Yes | 0 | 18 | 10
NeronetTrainer | Version 1 | Sprint 4 | 764159 | US16, As a user, I want to have example use cases that I can study | Done | Teemu Blomqvist |  |  | 3 | 4 | [7 empty] | 5 | Bugfixing | Teemu Blomqvist | 2016-02-05 18:47 |  |  | Yes | 0 | 18 | 10
NeronetTrainer | Version 1 | Sprint 4 | 764159 | US16, As a user, I want to have example use cases that I can study | Done | Teemu Blomqvist |  |  | 3 | 4 | [7 empty] | 5 | Bugfixing | Matias Pitkänen | 2016-02-05 18:47 |  |  | Yes | 0 | 18 | 10
NeronetTrainer | Version 1 | Sprint 4 | 764159 | US16, As a user, I want to have example use cases that I can study | Done | Teemu Blomqvist |  |  | 3 | 4 | [7 empty] | 4 | Polishing start_guide.rst | Teemu Blomqvist | 2016-02-26 17:58 |  |  | Yes | 0 | 18 | 10
NeronetTrainer | Version 1 | Sprint 4 | 764159 | US16, As a user, I want to have example use cases that I can study | Done | Teemu Blomqvist |  |  | 3 | 4 | [7 empty] | 0.3 | peer review | Samuel Marisa | 2016-02-28 22:10 |  |  | Yes | 0 | 18 | 10
NeronetTrainer | Version 1 | Sprint 4 | 764159 | US16, As a user, I want to have example use cases that I can study | Done | Teemu Blomqvist |  |  | 3 | 4 | [7 empty] | 2 | Finishing the example in the user guide | Matias Pitkänen | 2016-02-12 19:14 |  |  | Yes | 0 | 18 | 10
NeronetTrainer | Version 1 | Sprint 4 | 764159 | US16, As a user, I want to have example use cases that I can study | Done | Teemu Blomqvist |  |  | 3 | 4 | [7 empty] | 3.5 | Tried another experiment, ended up fixing bugs | Teemu Blomqvist | 2016-02-03 18:14 |  |  | Yes | 0 | 18 | 10
NeronetTrainer | Version 1 | Sprint 4 | 764159 | US16, As a user, I want to have example use cases that I can study | Done | Teemu Blomqvist |  |  | 3 | 4 | [7 empty] | 3.5 | Tried another experiment, ended up fixing bugs | Matias Pitkänen | 2016-02-03 18:14 |  |  | Yes | 0 | 18 | 10
NeronetTrainer | Version 1 | Sprint 4 | 764200 | US17, As a user I want to use basic functionalities via GUI | Done | Tuomo Perä |  |  | 2 | 3 | [7 empty] | 4 |  | Tuomo Perä | 2016-02-26 20:30 |  |  | Yes | 2 | 13 | 5
NeronetTrainer | Version 1 | Sprint 4 | 764200 | US17, As a user I want to use basic functionalities via GUI | Done | Tuomo Perä |  |  | 2 | 3 | [7 empty] | 0.4 | peer review | Tuomo Perä | 2016-02-28 22:30 |  |  | Yes | 2 | 13 | 5
NeronetTrainer | Version 1 | Sprint 4 | 764200 | US17, As a user I want to use basic functionalities via GUI | Done | Tuomo Perä |  |  | 2 | 3 | [7 empty] | 2 |  | Tuomo Perä | 2016-02-12 23:24 |  |  | Yes | 2 | 13 | 5
NeronetTrainer | Version 1 | Sprint 4 | 764200 | US17, As a user I want to use basic functionalities via GUI | Done | Tuomo Perä |  |  | 2 | 3 | [7 empty] | 6 |  | Tuomo Perä | 2016-02-10 01:39 |  |  | Yes | 2 | 13 | 5
NeronetTrainer | Version 1 | Sprint 4 | 764200 | US17, As a user I want to use basic functionalities via GUI | Done | Tuomo Perä |  |  | 2 | 3 | [7 empty] | 0.4 | peer review | Teemu Blomqvist | 2016-02-28 22:30 |  |  | Yes | 2 | 13 | 5
NeronetTrainer | Version 1 | Sprint 4 | 764200 | US17, As a user I want to use basic functionalities via GUI | Done | Tuomo Perä |  |  | 2 | 3 | [7 empty] | 0.4 | peer review | Samuel Marisa | 2016-02-28 22:30 |  |  | Yes | 2 | 13 | 5
NeronetTrainer | Version 1 | Sprint 4 | 764200 | US17, As a user I want to use basic functionalities via GUI | Done | Tuomo Perä |  |  | 2 | 3 | [7 empty] | 0.4 | peer review | Iiro Tähkä | 2016-02-28 22:30 |  |  | Yes | 2 | 13 | 5
NeronetTrainer | Version 1 | Sprint 4 | 764200 | US17, As a user I want to use basic functionalities via GUI | Done | Tuomo Perä |  |  | 2 | 3 | [7 empty] | 6 |  | Tuomo Perä | 2016-02-24 23:24 |  |  | Yes | 2 | 13 | 5
NeronetTrainer | Version 1 | Sprint 4 | 764200 | US17, As a user I want to use basic functionalities via GUI | Done | Tuomo Perä |  |  | 2 | 3 | [7 empty] | 6 |  | Tuomo Perä | 2016-02-03 01:39 |  |  | Yes | 2 | 13 | 5
NeronetTrainer | Version 1 | Sprint 4 | 764199 | US18, As a user I want to be able to easily visualise variable changes by time | Done | Iiro Tähkä |  |  | 3 | 3 | [7 empty] | 1.1 | Peer review | Iiro Tähkä | 2016-02-28 23:29 |  |  | Yes | 3 | 14 | 6
NeronetTrainer | Version 1 | Sprint 4 | 764199 | US18, As a user I want to be able to easily visualise variable changes by time | Done | Iiro Tähkä |  |  | 3 | 3 | [7 empty] | 1.1 | Peer review | Teemu Blomqvist | 2016-02-28 23:29 |  |  | Yes | 3 | 14 | 6
NeronetTrainer | Version 1 | Sprint 4 | 764199 | US18, As a user I want to be able to easily visualise variable changes by time | Done | Iiro Tähkä |  |  | 3 | 3 | [7 empty] | 2 | Consulted Iiro | Samuel Marisa | 2016-02-05 18:00 |  |  | Yes | 3 | 14 | 6
NeronetTrainer | Version 1 | Sprint 4 | 764199 | US18, As a user I want to be able to easily visualise variable changes by time | Done | Iiro Tähkä |  |  | 3 | 3 | [7 empty] | 1.1 | Peer review | Samuel Marisa | 2016-02-28 23:29 |  |  | Yes | 3 | 14 | 6
NeronetTrainer | Version 1 | Sprint 4 | 764199 | US18, As a user I want to be able to easily visualise variable changes by time | Done | Iiro Tähkä |  |  | 3 | 3 |  |  | 562605 | Development - Data plotting | Done | Iiro Tähkä |  | 2 | Improvements | Iiro Tähkä | 2016-02-26 18:13 | 0 | 2 | Yes | 3 | 14 | 6
NeronetTrainer | Version 1 | Sprint 4 | 764199 | US18, As a user I want to be able to easily visualise variable changes by time | Done | Iiro Tähkä |  |  | 3 | 3 |  |  | 562605 | Development - Data plotting | Done | Iiro Tähkä |  | 1 |  | Iiro Tähkä | 2016-02-24 21:00 | 0 | 2 | Yes | 3 | 14 | 6
NeronetTrainer | Version 1 | Sprint 4 | 764199 | US18, As a user I want to be able to easily visualise variable changes by time | Done | Iiro Tähkä |  |  | 3 | 3 |  |  | 562603 | Development - Output format specification | Done | Iiro Tähkä |  | 2 | Developed a dynamic import system for user defined output readers | Iiro Tähkä | 2016-02-24 19:00 | 0 | 1 | Yes | 3 | 14 | 6
NeronetTrainer | Version 1 | Sprint 4 | 764199 | US18, As a user I want to be able to easily visualise variable changes by time | Done | Iiro Tähkä |  |  | 3 | 3 |  |  | 562604 | Development - Output parsing | Done | Iiro Tähkä |  | 1 |  | Iiro Tähkä | 2016-02-24 20:00 | 0 | 1 | Yes | 3 | 14 | 6
NeronetTrainer | Version 1 | Sprint 4 | 764199 | US18, As a user I want to be able to easily visualise variable changes by time | Done | Iiro Tähkä |  |  | 3 | 3 |  |  | 562604 | Development - Output parsing | Done | Iiro Tähkä |  | 1 | improvements | Iiro Tähkä | 2016-02-26 15:13 | 0 | 1 | Yes | 3 | 14 | 6
NeronetTrainer | Version 1 | Sprint 4 | 764199 | US18, As a user I want to be able to easily visualise variable changes by time | Done | Iiro Tähkä |  |  | 3 | 3 |  |  | 562604 | Development - Output parsing | Done | Iiro Tähkä |  | 2 |  | Iiro Tähkä | 2016-02-05 20:03 | 0 | 1 | Yes | 3 | 14 | 6
NeronetTrainer | Version 1 | Sprint 4 | 764199 | US18, As a user I want to be able to easily visualise variable changes by time | Done | Iiro Tähkä |  |  | 3 | 3 |  |  | 562600 | Planning | Done | Iiro Tähkä |  | 2 |  | Iiro Tähkä | 2016-02-24 17:39 | 0 | 3 | Yes | 3 | 14 | 6
NeronetTrainer | Version 1 | Sprint 4 | 764199 | US18, As a user I want to be able to easily visualise variable changes by time | Done | Iiro Tähkä |  |  | 3 | 3 |  |  | 562600 | Planning | Done | Iiro Tähkä |  | 1 | Initial planning and requests for feedback | Iiro Tähkä | 2016-02-03 19:08 | 0 | 3 | Yes | 3 | 14 | 6
NeronetTrainer | Version 1 | Sprint 4 | 764199 | US18, As a user I want to be able to easily visualise variable changes by time | Done | Iiro Tähkä |  |  | 3 | 3 |  |  | 562600 | Planning | Done | Iiro Tähkä |  | 2.5 | Additional planning | Iiro Tähkä | 2016-02-05 20:02 | 0 | 3 | Yes | 3 | 14 | 6
NeronetTrainer | Version 1 | Sprint 4 | 764199 | US18, As a user I want to be able to easily visualise variable changes by time | Done | Iiro Tähkä |  |  | 3 | 3 |  |  | 562608 | Study and installation of matplotlib | Done | Iiro Tähkä |  | 2 |  | Iiro Tähkä | 2016-02-03 19:06 | 0 | 2 | Yes | 3 | 14 | 6
NeronetTrainer | Version 1 | Sprint 4 | 764163 | US19, As a maintainer, I want a clear maintenance guide | Done | Matias Pitkänen |  |  | 2 | 3 | [7 empty] | 6 |  | Teemu Blomqvist | 2016-02-24 14:14 |  |  | Yes | 4 | 15 | 7
NeronetTrainer | Version 1 | Sprint 4 | 764163 | US19, As a maintainer, I want a clear maintenance guide | Done | Matias Pitkänen |  |  | 2 | 3 | [7 empty] | 1 | Added pypi tutorial to the technical overview | Matias Pitkänen | 2016-02-12 19:14 |  |  | Yes | 4 | 15 | 7
NeronetTrainer | Version 1 | Sprint 4 | 764163 | US19, As a maintainer, I want a clear maintenance guide | Done | Matias Pitkänen |  |  | 2 | 3 | [7 empty] | 6 |  | Matias Pitkänen | 2016-02-24 14:19 |  |  | Yes | 4 | 15 | 7
NeronetTrainer | Version 1 | Sprint 4 | 764160 | US20, As a user I want to have a helpful web community to help me out | Done | Joona Marjakangas |  |  | 2 | 3 | [7 empty] | 0.4 |  | Samuel Marisa | 2016-03-28 15:59 |  |  | Yes | 5 | 17 | 9
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 579693 | Enhance user experience based on feedback | Done | Tuomo Perä |  | 4.4 | Peer team testing and related bug fixing | Samuel Marisa | 2016-03-18 19:13 | 0 | 4
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 581592 | General discussion and planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.2 | daily scrum and progress check; planning | Samuel Marisa | 2016-03-09 19:53 | 0 | 10
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 581592 | General discussion and planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.2 | same as below | Teemu Blomqvist | 2016-03-09 19:55 | 0 | 10
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 581592 | General discussion and planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 4 | Planning for the peer test session | Teemu Blomqvist | 2016-03-16 14:00 | 0 | 10
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 581592 | General discussion and planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3 | Participated in the peer review | Teemu Blomqvist | 2016-03-18 20:24 | 0 | 10
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 581592 | General discussion and planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 3.5 | Sprint review and change and some other stuff I cant bother to mark elsewhere | Teemu Blomqvist | 2016-03-30 19:00 | 0 | 10
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 581592 | General discussion and planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | daily scrum, progress check and planning work | Samuel Marisa | 2016-03-11 19:00 | 0 | 10
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 581592 | General discussion and planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 4 | planning for the peer test session | Matias Pitkänen | 2016-03-16 17:41 | 0 | 10
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 581592 | General discussion and planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 4 | sprint review | Matias Pitkänen | 2016-03-30 18:21 | 0 | 10
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 577928 | Improve documentation | Done | Teemu Blomqvist |  | 2 |  | Teemu Blomqvist | 2016-03-02 14:03
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 577928 | Improve documentation | Done | Teemu Blomqvist |  | 2 | Improved start_guide.rst | Teemu Blomqvist | 2016-03-18 19:06
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 577928 | Improve documentation | Done | Teemu Blomqvist |  | 2 | Improving user manual | Joona Marjakangas | 2016-03-02 16:00
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 579897 | Learning diary | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2 | Did my learning diary | Teemu Blomqvist | 2016-03-09 19:54 | 0 | 8
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 579897 | Learning diary | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 2.5 | Did my learning diary entry | Samuel Marisa | 2016-03-05 23:40 | 0 | 8
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 578415 | Refactoring and general improvements | Done |  |  | 6 | Spent the day fixing bugs | Teemu Blomqvist | 2016-03-23 20:26
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 578379 | Review all artifacts | Done | Iiro Tähkä, Teemu Blomqvist, Tuomo Perä |  | 2.5 | Reviewed retrospectives, artifacts, notes and competitor materials. | Matias Pitkänen | 2016-03-02 20:00 | 0 | 2
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 578379 | Review all artifacts | Done | Iiro Tähkä, Teemu Blomqvist, Tuomo Perä |  | 2.5 | Reviewed retrospectives, artifacts, notes and competitor materials. | Joona Marjakangas | 2016-03-02 20:00 | 0 | 2
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 578379 | Review all artifacts | Done | Iiro Tähkä, Teemu Blomqvist, Tuomo Perä |  | 2.5 | Reviewed retrospectives, artifacts, notes and competitor materials. | Samuel Marisa | 2016-03-02 20:00 | 0 | 2
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 576823 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.9 | Planning/scheduling the rest of the course | Samuel Marisa | 2016-03-01 18:50 | 0 | 8
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 576823 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.1 | Sprint planning part 1 | Samuel Marisa | 2016-02-29 16:14 | 0 | 8
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 576823 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 0.2 | Discussed the sprint and plans with the team. | Samuel Marisa | 2016-03-02 20:20 | 0 | 8
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 576823 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.1 | Sprint planning part 1 | Joona Marjakangas | 2016-02-29 16:14 | 0 | 8
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 576823 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.1 | Sprint planning part 1 | Teemu Blomqvist | 2016-02-29 16:14 | 0 | 8
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 576823 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.1 | Sprint planning part 1 | Iiro Tähkä | 2016-02-29 16:14 | 0 | 8
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 576823 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.1 | Sprint planning part 1 | Tuomo Perä | 2016-02-29 16:14 | 0 | 8
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 576823 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.1 | Sprint planning part 1 | Pyry Takala | 2016-02-29 16:14 | 0 | 8
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 576823 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | 1.1 | Sprint planning part 1 | Matias Pitkänen | 2016-02-29 16:14 | 0 | 8
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 579654 | Sprint review | Done |  |  | 3 | Prepared for and organized the sprint review | Samuel Marisa | 2016-03-30 19:00
NeronetTrainer | Version 1 | Sprint 5 | 780623 | As a user I want to filter by parameters in the GUI table | Done | Tuomo Perä |  |  | 2 | 4 | [7 empty] | 3 |  | Tuomo Perä | 2016-03-02 20:31 |  |  | Yes | 6 | 10 | 14.7 | As a user, I want an interactive GUI to utilize Neroman easily.
NeronetTrainer | Version 1 | Sprint 5 | 780623 | As a user I want to filter by parameters in the GUI table | Done | Tuomo Perä |  |  | 2 | 4 | [7 empty] | 5 |  | Tuomo Perä | 2016-03-04 23:14 |  |  | Yes | 6 | 10 | 14.7 | As a user, I want an interactive GUI to utilize Neroman easily.
NeronetTrainer | Version 1 | Sprint 5 | 780623 | As a user I want to filter by parameters in the GUI table | Done | Tuomo Perä |  |  | 2 | 4 | [7 empty] | 6 |  | Tuomo Perä | 2016-03-10 02:31 |  |  | Yes | 6 | 10 | 14.7 | As a user, I want an interactive GUI to utilize Neroman easily.
NeronetTrainer | Version 1 | Sprint 5 | 780623 | As a user I want to filter by parameters in the GUI table | Done | Tuomo Perä |  |  | 2 | 4 | [7 empty] | 5 |  | Tuomo Perä | 2016-03-12 02:31 |  |  | Yes | 6 | 10 | 14.7 | As a user, I want an interactive GUI to utilize Neroman easily.
NeronetTrainer | Version 1 | Sprint 5 | 780623 | As a user I want to filter by parameters in the GUI table | Done | Tuomo Perä |  |  | 2 | 4 | [7 empty] | 3 |  | Tuomo Perä | 2016-03-03 04:40 |  |  | Yes | 6 | 10 | 14.7 | As a user, I want an interactive GUI to utilize Neroman easily.
NeronetTrainer | Version 1 | Sprint 5 | 780623 | As a user I want to filter by parameters in the GUI table | Done | Tuomo Perä |  |  | 2 | 4 | [7 empty] | 1 |  | Tuomo Perä | 2016-03-03 15:07 |  |  | Yes | 6 | 10 | 14.7 | As a user, I want an interactive GUI to utilize Neroman easily.
NeronetTrainer | Version 1 | Sprint 5 | 780621 | As a user I want to have a big table with all experiments | Done | Tuomo Perä |  |  | 1 | 4 | [7 empty] | 5 |  | Tuomo Perä | 2016-03-18 19:24 |  |  | Yes | 7 | 11 | 14.8 | As a user, I want an interactive GUI to utilize Neroman easily.
NeronetTrainer | Version 1 | Sprint 5 | 780621 | As a user I want to have a big table with all experiments | Done | Tuomo Perä |  |  | 1 | 4 | [7 empty] | 1 |  | Tuomo Perä | 2016-03-13 19:24 |  |  | Yes | 7 | 11 | 14.8 | As a user, I want an interactive GUI to utilize Neroman easily.
NeronetTrainer | Version 1 | Sprint 5 | 780621 | As a user I want to have a big table with all experiments | Done | Tuomo Perä |  |  | 1 | 4 | [7 empty] | 6 |  | Tuomo Perä | 2016-03-16 19:23 |  |  | Yes | 7 | 11 | 14.8 | As a user, I want an interactive GUI to utilize Neroman easily.
NeronetTrainer | Version 1 | Sprint 5 | 780621 | As a user I want to have a big table with all experiments | Done | Tuomo Perä |  |  | 1 | 4 | [7 empty] | 3 |  | Tuomo Perä | 2016-03-02 20:30 |  |  | Yes | 7 | 11 | 14.8 | As a user, I want an interactive GUI to utilize Neroman easily.
NeronetTrainer | Version 1 | Sprint 5 | 780658 | As a user I want to see cluster resource info easily | Ready | Matias Pitkänen |  |  | 2 | 3 | [7 empty] | 4 | ready for peer review | Matias Pitkänen | 2016-03-11 18:25 |  |  | Yes | 1 | 7 | 1
NeronetTrainer | Version 1 | Sprint 5 | 780658 | As a user I want to see cluster resource info easily | Ready | Matias Pitkänen |  |  | 2 | 3 | [7 empty] | 5 |  | Matias Pitkänen | 2016-03-04 18:49 |  |  | Yes | 1 | 7 | 1
NeronetTrainer | Version 1 | Sprint 5 | 780658 | As a user I want to see cluster resource info easily | Ready | Matias Pitkänen |  |  | 2 | 3 | [7 empty] | 2.5 |  | Matias Pitkänen | 2016-03-02 18:09 |  |  | Yes | 1 | 7 | 1
NeronetTrainer | Version 1 | Sprint 5 | 780658 | As a user I want to see cluster resource info easily | Ready | Matias Pitkänen |  |  | 2 | 3 | [7 empty] | 6 |  | Matias Pitkänen | 2016-03-09 19:42 |  |  | Yes | 1 | 7 | 1
NeronetTrainer | Version 1 | Sprint 5 | 732149 | As a user, I want a cluster status report on individual clusters as well as an overview on all clusters | Done | Teemu Blomqvist |  |  | 2 | 2 | [7 empty] | 1 | Added %diskspace, %usedmemory to 'nerocli --status nodes' | Teemu Blomqvist | 2016-04-12 19:17 |  |  | Yes | 2 | 26 | 12.1 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 5 | 732149 | As a user, I want a cluster status report on individual clusters as well as an overview on all clusters | Done | Teemu Blomqvist |  |  | 2 | 2 | [7 empty] | 3.5 | Mostly finished the story, missing some small things | Teemu Blomqvist | 2016-03-30 16:28 |  |  | Yes | 2 | 26 | 12.1 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 5 | 732149 | As a user, I want a cluster status report on individual clusters as well as an overview on all clusters | Done | Teemu Blomqvist |  |  | 2 | 2 | [7 empty] | 2.4 | Figuring out what to do | Teemu Blomqvist | 2016-03-09 19:56 |  |  | Yes | 2 | 26 | 12.1 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 5 | 783760 | As a user, I want to open plots directly from the GUI | Done | Iiro Tähkä, Tuomo Perä |  |  | 1 | 3 | [7 empty] | 6 |  | Tuomo Perä | 2016-03-30 17:54 |  |  | Yes | 0 | 6 | 14.0 | As a user, I want an interactive GUI to utilize Neroman easily.
NeronetTrainer | Version 1 | Sprint 5 | 783760 | As a user, I want to open plots directly from the GUI | Done | Iiro Tähkä, Tuomo Perä |  |  | 1 | 3 | [7 empty] | 4 |  | Tuomo Perä | 2016-03-24 00:36 |  |  | Yes | 0 | 6 | 14.0 | As a user, I want an interactive GUI to utilize Neroman easily.
NeronetTrainer | Version 1 | Sprint 5 | 770053 | US24: As a user, I want to cancel a submitted experiment | Done | Joona Marjakangas |  |  | 2 | 3 |  |  | 579621 | Communication between neroman and - mum | Done | Joona Marjakangas |  | 1 | Work on sending messages from man to mum | Joona Marjakangas | 2016-03-07 15:22 | 0 | 3 | Yes | 3 | 12 | 4
NeronetTrainer | Version 1 | Sprint 5 | 770053 | US24: As a user, I want to cancel a submitted experiment | Done | Joona Marjakangas |  |  | 2 | 3 |  |  | 579621 | Communication between neroman and - mum | Done | Joona Marjakangas |  | 2 | Finished | Joona Marjakangas | 2016-03-09 19:00 | 0 | 3 | Yes | 3 | 12 | 4
NeronetTrainer | Version 1 | Sprint 5 | 770053 | US24: As a user, I want to cancel a submitted experiment | Done | Joona Marjakangas |  |  | 2 | 3 |  |  | 582497 | Improving error messages and debugging | Done | Joona Marjakangas |  | 3 | Finished | Joona Marjakangas | 2016-03-23 16:00 | 0 | 2 | Yes | 3 | 12 | 4
NeronetTrainer | Version 1 | Sprint 5 | 770053 | US24: As a user, I want to cancel a submitted experiment | Done | Joona Marjakangas |  |  | 2 | 3 |  |  | 579591 | Planning | Done | Joona Marjakangas |  | 1.5 | Planning | Joona Marjakangas | 2016-03-02 17:30 |  |  | Yes | 3 | 12 | 4
NeronetTrainer | Version 1 | Sprint 5 | 770053 | US24: As a user, I want to cancel a submitted experiment | Done | Joona Marjakangas |  |  | 2 | 3 |  |  | 579620 | Work on communication between neromum and kids as well as between cli and neroman | Done | Joona Marjakangas |  | 3 | All else works except communication between man and mum | Joona Marjakangas | 2016-03-04 17:09 | 0 | 0 | Yes | 3 | 12 | 4
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 579116 | Check out imports | Done | Iiro Tähkä |  | 0.5 |  | Iiro Tähkä | 2016-03-04 01:24 | 0 | 1 | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 578096 | Improve Exception handling | Done | Iiro Tähkä |  | 6 | Improve on expetion handling | Iiro Tähkä | 2016-03-09 16:39 | 0 | 4 | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 578079 | Improve config parser config.yaml parsing | Ready | Iiro Tähkä |  | 8 | Implement thorough error checking | Iiro Tähkä | 2016-03-25 16:35 | 0 | 4 | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 578097 | Improve error messages | Not Started | Iiro Tähkä |  | 5 | Improve expetions | Iiro Tähkä | 2016-03-11 16:40 | 0 | 4 | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 578080 | Improve module importing -> Output parsing and plotting related code | Done | Iiro Tähkä |  | 1 | Polish plotting and output parsing | Iiro Tähkä | 2016-03-23 16:36 | 0 | 4 | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 578080 | Improve module importing -> Output parsing and plotting related code | Done | Iiro Tähkä |  | 2.5 |  | Iiro Tähkä | 2016-03-04 04:13 | 0 | 4 | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 578080 | Improve module importing -> Output parsing and plotting related code | Done | Iiro Tähkä |  | 2.5 | Added flexibility to output parsing and plotting | Iiro Tähkä | 2016-03-04 19:12 | 0 | 4 | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 579117 | Improve on stuff | Done | Iiro Tähkä |  | 1 | Improved dependencies | Iiro Tähkä | 2016-03-03 16:34 | 0 | 1.5 | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 579117 | Improve on stuff | Done | Iiro Tähkä |  | 0.5 | Moved neronet references from config parser to core | Iiro Tähkä | 2016-03-04 19:14 | 0 | 1.5 | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 578098 | Planning | Done | Iiro Tähkä |  | 1 | Additional planning | Iiro Tähkä | 2016-03-06 16:38 | 0 | 2 | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 578098 | Planning | Done | Iiro Tähkä |  | 1.5 | Plan out what should be done | Iiro Tähkä | 2016-03-02 16:50 | 0 | 2 | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 578098 | Planning | Done | Iiro Tähkä |  | 1.5 |  | Iiro Tähkä | 2016-03-04 19:11 | 0 | 2 | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 578098 | Planning | Done | Iiro Tähkä |  | 1 | planning | Iiro Tähkä | 2016-03-15 16:40 | 0 | 2 | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 578098 | Planning | Done | Iiro Tähkä |  | 1 | planning | Iiro Tähkä | 2016-03-17 16:40 | 0 | 2 | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 578075 | Refactor code (Move experiment and cluster classes to modules) MAKE SURE EVERYTHING WORKS | Done | Iiro Tähkä |  | 1 | Moved experiment module to its own module | Iiro Tähkä | 2016-03-04 00:11 | 0 | 2 | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 578075 | Refactor code (Move experiment and cluster classes to modules) MAKE SURE EVERYTHING WORKS | Done | Iiro Tähkä |  | 1 | Moved cluster to its own module | Iiro Tähkä | 2016-03-04 00:54 | 0 | 2 | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 578095 | Research what functions aren't safe (Don't raise exceptions when they should) | Done | Iiro Tähkä |  | 3 | Search for issues in code | Iiro Tähkä | 2016-03-03 16:39 | 0 | 4 | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 6 | [10 empty] | 591244 | General UX improvements and refactoring | Done | Samuel Marisa |  | 1.6 |  | Samuel Marisa | 2016-04-01 17:27
NeronetTrainer | Version 1 | Sprint 6 | [10 empty] | 591244 | General UX improvements and refactoring | Done | Samuel Marisa |  | 2.5 |  | Samuel Marisa | 2016-04-09 14:30
NeronetTrainer | Version 1 | Sprint 6 | [10 empty] | 591244 | General UX improvements and refactoring | Done | Samuel Marisa |  | 1 | Removed debug prints | Teemu Blomqvist | 2016-04-12 20:04
NeronetTrainer | Version 1 | Sprint 6 | [10 empty] | 590243 | General debugging, stress management and error handling | Done | Matias Pitkänen |  | 1.5 | Planning implementation proper logging | Teemu Blomqvist | 2016-04-01 17:26
NeronetTrainer | Version 1 | Sprint 6 | [10 empty] | 590219 | Prepare and practice the progress 3 review | Done | Joona Marjakangas |  | 2 | Progress report | Joona Marjakangas | 2016-04-12 00:30
NeronetTrainer | Version 1 | Sprint 6 | [10 empty] | 590219 | Prepare and practice the progress 3 review | Done | Joona Marjakangas |  | 1 | Preparing progress report | Joona Marjakangas | 2016-04-11 20:00
NeronetTrainer | Version 1 | Sprint 6 | [10 empty] | 590219 | Prepare and practice the progress 3 review | Done | Joona Marjakangas |  | 4 | Slides | Samuel Marisa | 2016-04-12 15:37
NeronetTrainer | Version 1 | Sprint 6 | [10 empty] | 590219 | Prepare and practice the progress 3 review | Done | Joona Marjakangas |  | 3 |  | Samuel Marisa | 2016-04-09 17:30
NeronetTrainer | Version 1 | Sprint 6 | [10 empty] | 590219 | Prepare and practice the progress 3 review | Done | Joona Marjakangas |  | 1 | Progress | Joona Marjakangas | 2016-04-12 07:58
NeronetTrainer | Version 1 | Sprint 6 | [10 empty] | 590219 | Prepare and practice the progress 3 review | Done | Joona Marjakangas |  | 5 | Preparing the progress report | Joona Marjakangas | 2016-04-09 18:00
NeronetTrainer | Version 1 | Sprint 6 | [10 empty] | 591242 | Retrospective | Done | Samuel Marisa |  | 1.5 |  | Samuel Marisa | 2016-04-01 17:26 | 0 | 1
NeronetTrainer | Version 1 | Sprint 6 | [10 empty] | 591242 | Retrospective | Done | Samuel Marisa |  | 1.5 |  | Teemu Blomqvist | 2016-04-01 17:26 | 0 | 1
NeronetTrainer | Version 1 | Sprint 6 | [10 empty] | 591243 | Test session charter | Done | Samuel Marisa |  | 1 |  | Teemu Blomqvist | 2016-04-01 17:25
NeronetTrainer | Version 1 | Sprint 6 | [10 empty] | 591243 | Test session charter | Done | Samuel Marisa |  | 1 |  | Samuel Marisa | 2016-04-01 17:25
NeronetTrainer | Version 1 | Sprint 6 | 796538 | As a user I want an improved manual | Done | Iiro Tähkä, Joona Marjakangas | [11 empty] | 2 | Improving manual | Joona Marjakangas | 2016-04-09 12:00 |  |  | Yes | 3 | 3 | -6
NeronetTrainer | Version 1 | Sprint 6 | 796538 | As a user I want an improved manual | Done | Iiro Tähkä, Joona Marjakangas | [11 empty] | 6 | Work on user manual plotting and output reading | Iiro Tähkä | 2016-04-08 20:30 |  |  | Yes | 3 | 3 | -6
NeronetTrainer | Version 1 | Sprint 6 | 796538 | As a user I want an improved manual | Done | Iiro Tähkä, Joona Marjakangas | [11 empty] | 2 |  | Matias Pitkänen | 2016-04-10 14:01 |  |  | Yes | 3 | 3 | -6
NeronetTrainer | Version 1 | Sprint 6 | 796538 | As a user I want an improved manual | Done | Iiro Tähkä, Joona Marjakangas | [11 empty] | 4 | updated user manual | Matias Pitkänen | 2016-04-01 16:48 |  |  | Yes | 3 | 3 | -6
NeronetTrainer | Version 1 | Sprint 6 | 796536 | As a user I want to add experiments from the GUI | Done | Tuomo Perä | [11 empty] | 3 | Add experiments | Tuomo Perä | 2016-04-01 16:31 |  |  | Yes | 5 | 5 | -4
NeronetTrainer | Version 1 | Sprint 6 | 796536 | As a user I want to add experiments from the GUI | Done | Tuomo Perä | [11 empty] | 2.5 | Error handling | Tuomo Perä | 2016-04-09 16:31 |  |  | Yes | 5 | 5 | -4
NeronetTrainer | Version 1 | Sprint 6 | 796539 | As a user I want to combine different experiments in a plot | Done | Iiro Tähkä | [11 empty] | 6 | Finish plot combination | Iiro Tähkä | 2016-04-12 17:44 |  |  | Yes | 2 | 2 | -7
NeronetTrainer | Version 1 | Sprint 6 | 796539 | As a user I want to combine different experiments in a plot | Done | Iiro Tähkä | [11 empty] | 3 | Improve plotting error handling | Iiro Tähkä | 2016-04-09 16:32 |  |  | Yes | 2 | 2 | -7
NeronetTrainer | Version 1 | Sprint 6 | 800920 | As a user I want to see log info at experiment status reports | Done | Samuel Marisa | [11 empty] | 3 |  | Samuel Marisa | 2016-04-10 15:35 |  |  | Yes | 0 | 0 | -10

## Stories
Product | Project | Iteration | Story Id | Story | Story State (current) | Story Responsibles | Story labels | Story Description | Story points | Story value | Story depends on | Story required by | Leaf Story | Iteration rank | Backlog rank | Hierarchy position | Parent stories
NeronetTrainer | Version 1 |  | 719296 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal. | Not Started |  | epic | [5 empty] | Yes |  | 0 | 12
NeronetTrainer | Version 1 |  | 717302 | As a user, I want a collections status report so that I can get an overview of collections. | Not Started |  |  |  | 2 | 2 | US15, As a user, I want a status report so that I can get an overview. |  | Yes |  | 42 | 12.18 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 |  | 717304 | As a user, I want an interactive GUI to utilize Neroman easily. | Not Started |  | epic |  |  | 5 |  |  | Yes |  | 21 | 14
NeronetTrainer | Version 1 |  | 732147 | As a user, I want neronet to be able to automatically divide the work between clusters | Not Started |  |  |  | 3 | 2 |  |  | Yes |  | 28 | 12.3 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 |  | 764161 | As a user, I want the product to be supported also in the future | Not Started |  | EPIC |  |  | 3 |  |  | Yes |  | 16 | 8
NeronetTrainer | Version 1 |  | 717305 | As a user, I want to be able to backup and extract the experiments data files manually | Not Started |  |  |  | 1 | 3 |  |  | Yes |  | 44 | 12.20 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 |  | 751949 | As a user, I want to configure clusters | Done | Tuomo Perä |  |  | 3 |  |  |  | Yes |  | 21 | 14.3 | As a user, I want an interactive GUI to utilize Neroman easily.
NeronetTrainer | Version 1 |  | 751952 | As a user, I want to configure experiments | Not Started | Tuomo Perä | EPIC | [5 empty] | Yes |  | 20 | 14.2 | As a user, I want an interactive GUI to utilize Neroman easily.
NeronetTrainer | Version 1 |  | 717294 | As a user, I want to monitor experiment log output in real time so that I know what is going on. | Not Started |  |  |  | 5 | 3 |  |  | Yes |  | 40 | 12.16 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 |  | 751946 | As a user, I want to see status of individual experiments | Done | Tuomo Perä |  |  | 3 |  |  |  | Yes |  | 23 | 14.5 | As a user, I want an interactive GUI to utilize Neroman easily.
NeronetTrainer | Version 1 |  | 751947 | As a user, I want to setup preferences if there are none | Not Started | Tuomo Perä |  |  | 2 |  |  |  | Yes |  | 22 | 14.4 | As a user, I want an interactive GUI to utilize Neroman easily.
NeronetTrainer | Version 1 |  | 732148 | As a user, I want to specify batches of experiments using various arguments | Not Started |  |  |  | 3 | 2 |  |  | Yes |  | 27 | 12.2 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 |  | 717308 | As a user, I want to submit batches to be run so it is easier to deal with many experiments. | Not Started |  |  |  | 2 | 3 |  |  | Yes |  | 46 | 12.15 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 |  | 751953 | As a user, I want to submit experiments to clusters | Done | Tuomo Perä |  |  | 2 |  |  |  | Yes |  | 19 | 14.1 | As a user, I want an interactive GUI to utilize Neroman easily.
NeronetTrainer | Version 1 | Sprint 1 | 721490 | US1: As a user, I want a basic user guide that would cover the installation of Neronet and its use via CLI . | Done | Joona Marjakangas |  |  | 3 | 6 |  |  | Yes | 0 | 36 | 11
NeronetTrainer | Version 1 | Sprint 1 | 721455 | US2: As a user, I want to specify clusters by address and type to specify my computing resources. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 1 | 3 |  |  | Yes | 1 | 38 | 12.11 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717298 | US3: As a user, I want to specify experiments by name, files and parameters. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | Yes | 2 | 39 | 12.12 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721468 | US4: As a user, I want to submit individual experiments to unmanaged nodes. | Done | Tuomo Perä, Matias Pitkänen |  |  | 5 | 6 |  |  | Yes | 3 | 37 | 12.13 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717303 | US5: As a user, I want an experiment status report so that I can review experiment status details. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | Yes | 4 | 41 | 12.17 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732143 | US10, As a user, I want the program enable easy setup | Done | Teemu Blomqvist, Matias Pitkänen |  |  | 4 | 6 |  |  | Yes | 4 | 32 | 12.7 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732142 | US6, As a user, I want to set my preferences (name, email, default cluster) | Done | Joona Marjakangas |  |  | 2 | 5 |  |  | Yes | 1 | 33 | 12.8 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 734098 | US7, As a user, I want my experiment config attributes to support generation of value combinations | Done | Joona Marjakangas, Iiro Tähkä |  |  | 1 | 6 |  |  | Yes | 2 | 25 | 12.0 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732144 | US8, As a user, I want my experiment specifications to be able to inherit properties | Done | Joona Marjakangas, Iiro Tähkä |  |  | 2 | 6 |  |  | Yes | 3 | 31 | 12.6 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 734099 | US9, As a user, I want to see a basic status report in the GUI | Done | Tuomo Perä |  |  | 3 | 4 |  |  | Yes | 0 | 24 | 14.6 | As a user, I want an interactive GUI to utilize Neroman easily.
NeronetTrainer | Version 1 | Sprint 3 | 732138 | US11, As a user, I want to save important information about my clusters | Done | Teemu Blomqvist, Matias Pitkänen |  |  | 1 | 4 |  |  | Yes | 0 | 35 | 12.10 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 3 | 732139 | US12, As a user, I want to group my clusters | Done | Joona Marjakangas |  |  | 1 | 4 |  |  | Yes | 1 | 34 | 12.9 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 3 | 732146 | US13, As a user, I want to delete obsolete versions of my experiments | Done | Iiro Tähkä |  |  | 1 | 4 |  |  | Yes | 2 | 29 | 12.4 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 3 | 732145 | US14, As a user, I want configurable criteria for experiment warnings and autotermination | Done | Joona Marjakangas |  |  | 4 | 4 |  |  | Yes | 3 | 30 | 12.5 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 3 | 717301 | US15, As a user, I want a status report so that I can get an overview. | Done | Iiro Tähkä |  |  | 1 | 5 |  | As a user, I want a collections status report so that I can get an overview of collections. | Yes | 4 | 43 | 12.19 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 4 | 717307 | US 21, As a user, I want to submit individual experiments to be run on Slurm clusters. | Deferred |  |  |  | 5 | 3 |  |  | Yes | 1 | 45 | 12.14 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 4 | 764159 | US16, As a user, I want to have example use cases that I can study | Done | Teemu Blomqvist |  |  | 3 | 4 |  |  | Yes | 0 | 18 | 10
NeronetTrainer | Version 1 | Sprint 4 | 764200 | US17, As a user I want to use basic functionalities via GUI | Done | Tuomo Perä |  |  | 2 | 3 |  |  | Yes | 2 | 13 | 5
NeronetTrainer | Version 1 | Sprint 4 | 764199 | US18, As a user I want to be able to easily visualise variable changes by time | Done | Iiro Tähkä |  |  | 3 | 3 |  |  | Yes | 3 | 14 | 6
NeronetTrainer | Version 1 | Sprint 4 | 764163 | US19, As a maintainer, I want a clear maintenance guide | Done | Matias Pitkänen |  |  | 2 | 3 |  |  | Yes | 4 | 15 | 7
NeronetTrainer | Version 1 | Sprint 4 | 764160 | US20, As a user I want to have a helpful web community to help me out | Done | Joona Marjakangas |  |  | 2 | 3 |  |  | Yes | 5 | 17 | 9
NeronetTrainer | Version 1 | Sprint 5 | 780623 | As a user I want to filter by parameters in the GUI table | Done | Tuomo Perä |  |  | 2 | 4 |  |  | Yes | 6 | 10 | 14.7 | As a user, I want an interactive GUI to utilize Neroman easily.
NeronetTrainer | Version 1 | Sprint 5 | 780621 | As a user I want to have a big table with all experiments | Done | Tuomo Perä |  |  | 1 | 4 |  |  | Yes | 7 | 11 | 14.8 | As a user, I want an interactive GUI to utilize Neroman easily.
NeronetTrainer | Version 1 | Sprint 5 | 780658 | As a user I want to see cluster resource info easily | Ready | Matias Pitkänen |  |  | 2 | 3 |  |  | Yes | 1 | 7 | 1
NeronetTrainer | Version 1 | Sprint 5 | 732149 | As a user, I want a cluster status report on individual clusters as well as an overview on all clusters | Done | Teemu Blomqvist |  |  | 2 | 2 |  |  | Yes | 2 | 26 | 12.1 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 5 | 783760 | As a user, I want to open plots directly from the GUI | Done | Iiro Tähkä, Tuomo Perä |  |  | 1 | 3 |  |  | Yes | 0 | 6 | 14.0 | As a user, I want an interactive GUI to utilize Neroman easily.
NeronetTrainer | Version 1 | Sprint 5 | 770053 | US24: As a user, I want to cancel a submitted experiment | Done | Joona Marjakangas |  |  | 2 | 3 |  |  | Yes | 3 | 12 | 4
NeronetTrainer | Version 1 | Sprint 5 | 780650 | US25: As a user I want to use the tool collaboratively | Deferred | Joona Marjakangas, Tuomo Perä, Matias Pitkänen |  |  | 5 | 4 |  |  | Yes | 4 | 8 | 2
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 6 | 796540 | As a user I want a clear introductory video | Pending | Joona Marjakangas, Samuel Marisa | [6 empty] | Yes | 1 | 1 | -8
NeronetTrainer | Version 1 | Sprint 6 | 796538 | As a user I want an improved manual | Done | Joona Marjakangas, Iiro Tähkä | [6 empty] | Yes | 3 | 3 | -6
NeronetTrainer | Version 1 | Sprint 6 | 796536 | As a user I want to add experiments from the GUI | Done | Tuomo Perä | [6 empty] | Yes | 5 | 5 | -4
NeronetTrainer | Version 1 | Sprint 6 | 796539 | As a user I want to combine different experiments in a plot | Done | Iiro Tähkä | [6 empty] | Yes | 2 | 2 | -7
NeronetTrainer | Version 1 | Sprint 6 | 800920 | As a user I want to see log info at experiment status reports | Done | Samuel Marisa | [6 empty] | Yes | 0 | 0 | -10
NeronetTrainer | Version 1 | Sprint 6 | 796537 | As a user I want to see node disk space easily | Done | Teemu Blomqvist | [6 empty] | Yes | 4 | 4 | -5

## Tasks
Product | Project | Iteration | Story Id | Story | Story State (current) | Story Responsibles | Story labels | Story Description | Story points | Story value | Story depends on | Story required by | Task Id | Task | Task State (current) | Task Responsibles | Task Description | Leaf Story | Iteration rank | Backlog rank | Hierarchy position | Parent stories
[13 empty] | 586066 | Peer group testing | Not Started | Matias Pitkänen
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518994 | Analyse projects | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518964 | Build team | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Presprint | [10 empty] | 519000 | Choose project | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Presprint | [10 empty] | 518962 | Recruit team members | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519342 | Communicate the process and schedule | Done | Samuel Marisa
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519035 | Develop a basic prototype | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519699 | Discuss plans and architecture with systems experts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519034 | Perform a market analysis | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 520459 | Prepare an initial backlog for sprint 1 | Done | Pyry Takala, Samuel Marisa
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519003 | Prepare initial artifacts | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 523744 | Present sprint 0 results to Coach | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 0 | [10 empty] | 519001 | Understand and initialize project | Done | Iiro Tähkä, Joona Marjakangas, Juho Pekkinen, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523750 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523805 | Learning diary | In Progress | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523746 | Restructuring the project repo | Done
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523749 | Setting up a documentation system | Done
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523747 | Setting up a testing framework | Done
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523745 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523752 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523751 | Sprint review | Done | Eero Laukkanen, Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 1 | [10 empty] | 523748 | Testing Neronet in Triton | Done
NeronetTrainer | Version 1 | Sprint 1 | 721490 | US1: As a user, I want a basic user guide that would cover the installation of Neronet and its use via CLI . | Done | Joona Marjakangas |  |  | 3 | 6 |  |  | 530790 | Adding Introduction and the list of contents and proofreading CLI | Done | Joona Marjakangas |  | Yes | 0 | 36 | 11
NeronetTrainer | Version 1 | Sprint 1 | 721490 | US1: As a user, I want a basic user guide that would cover the installation of Neronet and its use via CLI . | Done | Joona Marjakangas |  |  | 3 | 6 |  |  | 530790 | Adding Introduction and the list of contents and proofreading CLI | Done | Joona Marjakangas |  | Yes | 0 | 36 | 11
NeronetTrainer | Version 1 | Sprint 1 | 721490 | US1: As a user, I want a basic user guide that would cover the installation of Neronet and its use via CLI . | Done | Joona Marjakangas |  |  | 3 | 6 |  |  | 527103 | Implement CLI user guide | Done | Joona Marjakangas |  | Yes | 0 | 36 | 11
NeronetTrainer | Version 1 | Sprint 1 | 721490 | US1: As a user, I want a basic user guide that would cover the installation of Neronet and its use via CLI . | Done | Joona Marjakangas |  |  | 3 | 6 |  |  | 527103 | Implement CLI user guide | Done | Joona Marjakangas |  | Yes | 0 | 36 | 11
NeronetTrainer | Version 1 | Sprint 1 | 721490 | US1: As a user, I want a basic user guide that would cover the installation of Neronet and its use via CLI . | Done | Joona Marjakangas |  |  | 3 | 6 |  |  | 527104 | Implement GUI user guide | Done | Joona Marjakangas |  | Yes | 0 | 36 | 11
NeronetTrainer | Version 1 | Sprint 1 | 721490 | US1: As a user, I want a basic user guide that would cover the installation of Neronet and its use via CLI . | Done | Joona Marjakangas |  |  | 3 | 6 |  |  | 527104 | Implement GUI user guide | Done | Joona Marjakangas |  | Yes | 0 | 36 | 11
NeronetTrainer | Version 1 | Sprint 1 | 721490 | US1: As a user, I want a basic user guide that would cover the installation of Neronet and its use via CLI . | Done | Joona Marjakangas |  |  | 3 | 6 |  |  | 525373 | Peer review | Done | Iiro Tähkä, Teemu Blomqvist |  | Yes | 0 | 36 | 11
NeronetTrainer | Version 1 | Sprint 1 | 721490 | US1: As a user, I want a basic user guide that would cover the installation of Neronet and its use via CLI . | Done | Joona Marjakangas |  |  | 3 | 6 |  |  | 525373 | Peer review | Done | Iiro Tähkä, Teemu Blomqvist |  | Yes | 0 | 36 | 11
NeronetTrainer | Version 1 | Sprint 1 | 721490 | US1: As a user, I want a basic user guide that would cover the installation of Neronet and its use via CLI . | Done | Joona Marjakangas |  |  | 3 | 6 |  |  | 525372 | Plan structure | Done | Joona Marjakangas |  | Yes | 0 | 36 | 11
NeronetTrainer | Version 1 | Sprint 1 | 721490 | US1: As a user, I want a basic user guide that would cover the installation of Neronet and its use via CLI . | Done | Joona Marjakangas |  |  | 3 | 6 |  |  | 525372 | Plan structure | Done | Joona Marjakangas |  | Yes | 0 | 36 | 11
NeronetTrainer | Version 1 | Sprint 1 | 721455 | US2: As a user, I want to specify clusters by address and type to specify my computing resources. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 1 | 3 |  |  | 529979 | Development | Done | Iiro Tähkä, Teemu Blomqvist |  | Yes | 1 | 38 | 12.11 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721455 | US2: As a user, I want to specify clusters by address and type to specify my computing resources. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 1 | 3 |  |  | 529979 | Development | Done | Iiro Tähkä, Teemu Blomqvist |  | Yes | 1 | 38 | 12.11 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721455 | US2: As a user, I want to specify clusters by address and type to specify my computing resources. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 1 | 3 |  |  | 529981 | Documentation | Done | Iiro Tähkä, Teemu Blomqvist |  | Yes | 1 | 38 | 12.11 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721455 | US2: As a user, I want to specify clusters by address and type to specify my computing resources. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 1 | 3 |  |  | 529981 | Documentation | Done | Iiro Tähkä, Teemu Blomqvist |  | Yes | 1 | 38 | 12.11 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721455 | US2: As a user, I want to specify clusters by address and type to specify my computing resources. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 1 | 3 |  |  | 529978 | Planning | Done | Iiro Tähkä, Teemu Blomqvist |  | Yes | 1 | 38 | 12.11 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721455 | US2: As a user, I want to specify clusters by address and type to specify my computing resources. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 1 | 3 |  |  | 529978 | Planning | Done | Iiro Tähkä, Teemu Blomqvist |  | Yes | 1 | 38 | 12.11 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721455 | US2: As a user, I want to specify clusters by address and type to specify my computing resources. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 1 | 3 |  |  | 529982 | Review | Done | Matias Pitkänen, Tuomo Perä |  | Yes | 1 | 38 | 12.11 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721455 | US2: As a user, I want to specify clusters by address and type to specify my computing resources. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 1 | 3 |  |  | 529982 | Review | Done | Matias Pitkänen, Tuomo Perä |  | Yes | 1 | 38 | 12.11 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721455 | US2: As a user, I want to specify clusters by address and type to specify my computing resources. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 1 | 3 |  |  | 529980 | Testing | Done | Iiro Tähkä, Teemu Blomqvist |  | Yes | 1 | 38 | 12.11 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721455 | US2: As a user, I want to specify clusters by address and type to specify my computing resources. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 1 | 3 |  |  | 529980 | Testing | Done | Iiro Tähkä, Teemu Blomqvist |  | Yes | 1 | 38 | 12.11 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717298 | US3: As a user, I want to specify experiments by name, files and parameters. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 525382 | Development (Neroman) | Done | Iiro Tähkä, Teemu Blomqvist |  | Yes | 2 | 39 | 12.12 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717298 | US3: As a user, I want to specify experiments by name, files and parameters. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 525382 | Development (Neroman) | Done | Iiro Tähkä, Teemu Blomqvist |  | Yes | 2 | 39 | 12.12 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717298 | US3: As a user, I want to specify experiments by name, files and parameters. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 525384 | Documentation | Done | Iiro Tähkä, Teemu Blomqvist |  | Yes | 2 | 39 | 12.12 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717298 | US3: As a user, I want to specify experiments by name, files and parameters. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 525384 | Documentation | Done | Iiro Tähkä, Teemu Blomqvist |  | Yes | 2 | 39 | 12.12 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717298 | US3: As a user, I want to specify experiments by name, files and parameters. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 525381 | Planning | Done | Iiro Tähkä, Teemu Blomqvist |  | Yes | 2 | 39 | 12.12 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717298 | US3: As a user, I want to specify experiments by name, files and parameters. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 525381 | Planning | Done | Iiro Tähkä, Teemu Blomqvist |  | Yes | 2 | 39 | 12.12 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717298 | US3: As a user, I want to specify experiments by name, files and parameters. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 525385 | Review | Done | Matias Pitkänen, Tuomo Perä |  | Yes | 2 | 39 | 12.12 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717298 | US3: As a user, I want to specify experiments by name, files and parameters. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 525385 | Review | Done | Matias Pitkänen, Tuomo Perä |  | Yes | 2 | 39 | 12.12 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717298 | US3: As a user, I want to specify experiments by name, files and parameters. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 525383 | Testing | Done | Iiro Tähkä, Teemu Blomqvist |  | Yes | 2 | 39 | 12.12 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717298 | US3: As a user, I want to specify experiments by name, files and parameters. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 525383 | Testing | Done | Iiro Tähkä, Teemu Blomqvist |  | Yes | 2 | 39 | 12.12 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721468 | US4: As a user, I want to submit individual experiments to unmanaged nodes. | Done | Tuomo Perä, Matias Pitkänen |  |  | 5 | 6 |  |  | 530012 | Create tests | Done | Matias Pitkänen, Tuomo Perä |  | Yes | 3 | 37 | 12.13 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721468 | US4: As a user, I want to submit individual experiments to unmanaged nodes. | Done | Tuomo Perä, Matias Pitkänen |  |  | 5 | 6 |  |  | 530012 | Create tests | Done | Matias Pitkänen, Tuomo Perä |  | Yes | 3 | 37 | 12.13 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721468 | US4: As a user, I want to submit individual experiments to unmanaged nodes. | Done | Tuomo Perä, Matias Pitkänen |  |  | 5 | 6 |  |  | 530015 | Documentation | Done | Matias Pitkänen, Tuomo Perä |  | Yes | 3 | 37 | 12.13 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721468 | US4: As a user, I want to submit individual experiments to unmanaged nodes. | Done | Tuomo Perä, Matias Pitkänen |  |  | 5 | 6 |  |  | 530015 | Documentation | Done | Matias Pitkänen, Tuomo Perä |  | Yes | 3 | 37 | 12.13 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721468 | US4: As a user, I want to submit individual experiments to unmanaged nodes. | Done | Tuomo Perä, Matias Pitkänen |  |  | 5 | 6 |  |  | 529850 | Neroman can open a neromum using ssh | Done | Matias Pitkänen, Tuomo Perä |  | Yes | 3 | 37 | 12.13 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721468 | US4: As a user, I want to submit individual experiments to unmanaged nodes. | Done | Tuomo Perä, Matias Pitkänen |  |  | 5 | 6 |  |  | 529850 | Neroman can open a neromum using ssh | Done | Matias Pitkänen, Tuomo Perä |  | Yes | 3 | 37 | 12.13 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721468 | US4: As a user, I want to submit individual experiments to unmanaged nodes. | Done | Tuomo Perä, Matias Pitkänen |  |  | 5 | 6 |  |  | 529851 | Neroman can send files to nerokid to be run | Done | Matias Pitkänen, Tuomo Perä |  | Yes | 3 | 37 | 12.13 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721468 | US4: As a user, I want to submit individual experiments to unmanaged nodes. | Done | Tuomo Perä, Matias Pitkänen |  |  | 5 | 6 |  |  | 529851 | Neroman can send files to nerokid to be run | Done | Matias Pitkänen, Tuomo Perä |  | Yes | 3 | 37 | 12.13 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721468 | US4: As a user, I want to submit individual experiments to unmanaged nodes. | Done | Tuomo Perä, Matias Pitkänen |  |  | 5 | 6 |  |  | 529849 | Neromum can open a nerokid using sockets | Done | Matias Pitkänen, Tuomo Perä |  | Yes | 3 | 37 | 12.13 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721468 | US4: As a user, I want to submit individual experiments to unmanaged nodes. | Done | Tuomo Perä, Matias Pitkänen |  |  | 5 | 6 |  |  | 529849 | Neromum can open a nerokid using sockets | Done | Matias Pitkänen, Tuomo Perä |  | Yes | 3 | 37 | 12.13 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721468 | US4: As a user, I want to submit individual experiments to unmanaged nodes. | Done | Tuomo Perä, Matias Pitkänen |  |  | 5 | 6 |  |  | 530011 | Peer review | Done | Matias Pitkänen, Tuomo Perä |  | Yes | 3 | 37 | 12.13 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 721468 | US4: As a user, I want to submit individual experiments to unmanaged nodes. | Done | Tuomo Perä, Matias Pitkänen |  |  | 5 | 6 |  |  | 530011 | Peer review | Done | Matias Pitkänen, Tuomo Perä |  | Yes | 3 | 37 | 12.13 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717303 | US5: As a user, I want an experiment status report so that I can review experiment status details. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 530902 | Development | Done | Iiro Tähkä, Teemu Blomqvist |  | Yes | 4 | 41 | 12.17 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717303 | US5: As a user, I want an experiment status report so that I can review experiment status details. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 530902 | Development | Done | Iiro Tähkä, Teemu Blomqvist |  | Yes | 4 | 41 | 12.17 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717303 | US5: As a user, I want an experiment status report so that I can review experiment status details. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 530903 | Documentation | Done | Iiro Tähkä, Teemu Blomqvist |  | Yes | 4 | 41 | 12.17 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717303 | US5: As a user, I want an experiment status report so that I can review experiment status details. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 530903 | Documentation | Done | Iiro Tähkä, Teemu Blomqvist |  | Yes | 4 | 41 | 12.17 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717303 | US5: As a user, I want an experiment status report so that I can review experiment status details. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 530905 | Peer review | Done | Teemu Blomqvist |  | Yes | 4 | 41 | 12.17 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717303 | US5: As a user, I want an experiment status report so that I can review experiment status details. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 530905 | Peer review | Done | Teemu Blomqvist |  | Yes | 4 | 41 | 12.17 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717303 | US5: As a user, I want an experiment status report so that I can review experiment status details. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 530901 | Planning | Done | Iiro Tähkä, Teemu Blomqvist |  | Yes | 4 | 41 | 12.17 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717303 | US5: As a user, I want an experiment status report so that I can review experiment status details. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 530901 | Planning | Done | Iiro Tähkä, Teemu Blomqvist |  | Yes | 4 | 41 | 12.17 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717303 | US5: As a user, I want an experiment status report so that I can review experiment status details. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 530904 | Testing | Done | Iiro Tähkä, Teemu Blomqvist |  | Yes | 4 | 41 | 12.17 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 1 | 717303 | US5: As a user, I want an experiment status report so that I can review experiment status details. | Done | Iiro Tähkä, Teemu Blomqvist |  |  | 2 | 6 |  |  | 530904 | Testing | Done | Iiro Tähkä, Teemu Blomqvist |  | Yes | 4 | 41 | 12.17 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534528 | Full review of the previous increment | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534582 | General discussion, planning and coordination | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534590 | Setup readthedocs documentation | Done | Samuel Marisa, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534581 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534583 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534580 | Sprint review | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 550510 | System testing and debugging | Done | Joona Marjakangas
NeronetTrainer | Version 1 | Sprint 2 | [10 empty] | 534531 | Work toward an asynchronous daemon system | Done | Samuel Marisa, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 2 | 732142 | US6, As a user, I want to set my preferences (name, email, default cluster) | Done | Joona Marjakangas |  |  | 2 | 5 |  |  | 543621 | Implementing | Done | Joona Marjakangas |  | Yes | 1 | 33 | 12.8 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732142 | US6, As a user, I want to set my preferences (name, email, default cluster) | Done | Joona Marjakangas |  |  | 2 | 5 |  |  | 543621 | Implementing | Done | Joona Marjakangas |  | Yes | 1 | 33 | 12.8 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732142 | US6, As a user, I want to set my preferences (name, email, default cluster) | Done | Joona Marjakangas |  |  | 2 | 5 |  |  | 543619 | Peer review | Done | Matias Pitkänen |  | Yes | 1 | 33 | 12.8 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732142 | US6, As a user, I want to set my preferences (name, email, default cluster) | Done | Joona Marjakangas |  |  | 2 | 5 |  |  | 543619 | Peer review | Done | Matias Pitkänen |  | Yes | 1 | 33 | 12.8 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732142 | US6, As a user, I want to set my preferences (name, email, default cluster) | Done | Joona Marjakangas |  |  | 2 | 5 |  |  | 543618 | Planning | Done | Joona Marjakangas |  | Yes | 1 | 33 | 12.8 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732142 | US6, As a user, I want to set my preferences (name, email, default cluster) | Done | Joona Marjakangas |  |  | 2 | 5 |  |  | 543618 | Planning | Done | Joona Marjakangas |  | Yes | 1 | 33 | 12.8 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732142 | US6, As a user, I want to set my preferences (name, email, default cluster) | Done | Joona Marjakangas |  |  | 2 | 5 |  |  | 543620 | Testing | Done | Joona Marjakangas |  | Yes | 1 | 33 | 12.8 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732142 | US6, As a user, I want to set my preferences (name, email, default cluster) | Done | Joona Marjakangas |  |  | 2 | 5 |  |  | 543620 | Testing | Done | Joona Marjakangas |  | Yes | 1 | 33 | 12.8 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 734098 | US7, As a user, I want my experiment config attributes to support generation of value combinations | Done | Joona Marjakangas, Iiro Tähkä |  |  | 1 | 6 |  |  | 543614 | Implementing & Integrating | Done | Iiro Tähkä, Joona Marjakangas |  | Yes | 2 | 25 | 12.0 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 734098 | US7, As a user, I want my experiment config attributes to support generation of value combinations | Done | Iiro Tähkä, Joona Marjakangas |  |  | 1 | 6 |  |  | 543614 | Implementing & Integrating | Done | Iiro Tähkä, Joona Marjakangas |  | Yes | 2 | 25 | 12.0 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 734098 | US7, As a user, I want my experiment config attributes to support generation of value combinations | Done | Joona Marjakangas, Iiro Tähkä |  |  | 1 | 6 |  |  | 543611 | Peer review | Done |  |  | Yes | 2 | 25 | 12.0 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 734098 | US7, As a user, I want my experiment config attributes to support generation of value combinations | Done | Iiro Tähkä, Joona Marjakangas |  |  | 1 | 6 |  |  | 543611 | Peer review | Done |  |  | Yes | 2 | 25 | 12.0 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 734098 | US7, As a user, I want my experiment config attributes to support generation of value combinations | Done | Joona Marjakangas, Iiro Tähkä |  |  | 1 | 6 |  |  | 543613 | Planning | Done | Iiro Tähkä, Joona Marjakangas |  | Yes | 2 | 25 | 12.0 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 734098 | US7, As a user, I want my experiment config attributes to support generation of value combinations | Done | Iiro Tähkä, Joona Marjakangas |  |  | 1 | 6 |  |  | 543613 | Planning | Done | Iiro Tähkä, Joona Marjakangas |  | Yes | 2 | 25 | 12.0 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 734098 | US7, As a user, I want my experiment config attributes to support generation of value combinations | Done | Joona Marjakangas, Iiro Tähkä |  |  | 1 | 6 |  |  | 543612 | Testing | Done | Iiro Tähkä, Joona Marjakangas |  | Yes | 2 | 25 | 12.0 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 734098 | US7, As a user, I want my experiment config attributes to support generation of value combinations | Done | Iiro Tähkä, Joona Marjakangas |  |  | 1 | 6 |  |  | 543612 | Testing | Done | Iiro Tähkä, Joona Marjakangas |  | Yes | 2 | 25 | 12.0 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732144 | US8, As a user, I want my experiment specifications to be able to inherit properties | Done | Joona Marjakangas, Iiro Tähkä |  |  | 2 | 6 |  |  | 543617 | Implementing & Integrating | Done | Iiro Tähkä, Joona Marjakangas |  | Yes | 3 | 31 | 12.6 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732144 | US8, As a user, I want my experiment specifications to be able to inherit properties | Done | Iiro Tähkä, Joona Marjakangas |  |  | 2 | 6 |  |  | 543617 | Implementing & Integrating | Done | Iiro Tähkä, Joona Marjakangas |  | Yes | 3 | 31 | 12.6 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732144 | US8, As a user, I want my experiment specifications to be able to inherit properties | Done | Joona Marjakangas, Iiro Tähkä |  |  | 2 | 6 |  |  | 543610 | Peer review | Done |  |  | Yes | 3 | 31 | 12.6 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732144 | US8, As a user, I want my experiment specifications to be able to inherit properties | Done | Iiro Tähkä, Joona Marjakangas |  |  | 2 | 6 |  |  | 543610 | Peer review | Done |  |  | Yes | 3 | 31 | 12.6 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732144 | US8, As a user, I want my experiment specifications to be able to inherit properties | Done | Iiro Tähkä, Joona Marjakangas |  |  | 2 | 6 |  |  | 543615 | Planning | Done | Iiro Tähkä, Joona Marjakangas |  | Yes | 3 | 31 | 12.6 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732144 | US8, As a user, I want my experiment specifications to be able to inherit properties | Done | Joona Marjakangas, Iiro Tähkä |  |  | 2 | 6 |  |  | 543615 | Planning | Done | Iiro Tähkä, Joona Marjakangas |  | Yes | 3 | 31 | 12.6 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732144 | US8, As a user, I want my experiment specifications to be able to inherit properties | Done | Joona Marjakangas, Iiro Tähkä |  |  | 2 | 6 |  |  | 543616 | Testing | Done | Iiro Tähkä, Joona Marjakangas |  | Yes | 3 | 31 | 12.6 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 2 | 732144 | US8, As a user, I want my experiment specifications to be able to inherit properties | Done | Iiro Tähkä, Joona Marjakangas |  |  | 2 | 6 |  |  | 543616 | Testing | Done | Iiro Tähkä, Joona Marjakangas |  | Yes | 3 | 31 | 12.6 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 551555 | Comprehensive system testing | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 560789 | EES | Done | Joona Marjakangas, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550756 | Explore the possibilities and limitations of Qt and web based GUI solutions | Done | Tuomo Perä
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550757 | Finish asychronous system update | Done | Iiro Tähkä, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 551641 | General discussion | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 560141 | Quick start guide | Done | Joona Marjakangas
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 553988 | Random Coding Related Tasks | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550790 | Revert to Python2.7 (possibly support both) | Done | Joona Marjakangas, Matias Pitkänen, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550794 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Pyry Takala, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550791 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 3 | [10 empty] | 550793 | Sprint review | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 3 | 732139 | US12, As a user, I want to group my clusters | Done | Joona Marjakangas |  |  | 1 | 4 |  |  | 560787 | Enabling user to submit to a group | Done | Joona Marjakangas |  | Yes | 1 | 34 | 12.9 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 3 | 732139 | US12, As a user, I want to group my clusters | Done | Joona Marjakangas |  |  | 1 | 4 |  |  | 560787 | Enabling user to submit to a group | Done | Joona Marjakangas |  | Yes | 1 | 34 | 12.9 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 3 | 732139 | US12, As a user, I want to group my clusters | Done | Joona Marjakangas |  |  | 1 | 4 |  |  | 560788 | Peer review | Not Started |  |  | Yes | 1 | 34 | 12.9 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 3 | 732139 | US12, As a user, I want to group my clusters | Done | Joona Marjakangas |  |  | 1 | 4 |  |  | 560788 | Peer review | Not Started |  |  | Yes | 1 | 34 | 12.9 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 3 | 732145 | US14, As a user, I want configurable criteria for experiment warnings and autotermination | Done | Joona Marjakangas |  |  | 4 | 4 |  |  | 560137 | Creating and testing ExperimentWarning class to work with nerokid | Done | Joona Marjakangas |  | Yes | 3 | 30 | 12.5 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 3 | 732145 | US14, As a user, I want configurable criteria for experiment warnings and autotermination | Done | Joona Marjakangas |  |  | 4 | 4 |  |  | 560137 | Creating and testing ExperimentWarning class to work with nerokid | Done | Joona Marjakangas |  | Yes | 3 | 30 | 12.5 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 3 | 732145 | US14, As a user, I want configurable criteria for experiment warnings and autotermination | Done | Joona Marjakangas |  |  | 4 | 4 |  |  | 560138 | Enabling nerokid to send warnings and autoterminate together with the ExperimentWarning class | Done | Joona Marjakangas |  | Yes | 3 | 30 | 12.5 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 3 | 732145 | US14, As a user, I want configurable criteria for experiment warnings and autotermination | Done | Joona Marjakangas |  |  | 4 | 4 |  |  | 560138 | Enabling nerokid to send warnings and autoterminate together with the ExperimentWarning class | Done | Joona Marjakangas |  | Yes | 3 | 30 | 12.5 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 3 | 732145 | US14, As a user, I want configurable criteria for experiment warnings and autotermination | Done | Joona Marjakangas |  |  | 4 | 4 |  |  | 560139 | Enabling neroman to parse and send the required arguments to neromum and -kids | Done | Joona Marjakangas |  | Yes | 3 | 30 | 12.5 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 3 | 732145 | US14, As a user, I want configurable criteria for experiment warnings and autotermination | Done | Joona Marjakangas |  |  | 4 | 4 |  |  | 560139 | Enabling neroman to parse and send the required arguments to neromum and -kids | Done | Joona Marjakangas |  | Yes | 3 | 30 | 12.5 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 3 | 732145 | US14, As a user, I want configurable criteria for experiment warnings and autotermination | Done | Joona Marjakangas |  |  | 4 | 4 |  |  | 560140 | Peer review | Done | Joona Marjakangas |  | Yes | 3 | 30 | 12.5 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 3 | 732145 | US14, As a user, I want configurable criteria for experiment warnings and autotermination | Done | Joona Marjakangas |  |  | 4 | 4 |  |  | 560140 | Peer review | Done | Joona Marjakangas |  | Yes | 3 | 30 | 12.5 | As a user, I want a CLI to Neroman so that I can use its basic functionality via terminal.
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 561226 | Finding and supporting test users, marketing etc. | Done | Joona Marjakangas, Samuel Marisa
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 561225 | General appearance, marketability and clarity improvement | Done | Joona Marjakangas
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 567213 | General discussion and coordination, daily scrums | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 561224 | Implement improvements based on user feedback | Done | Samuel Marisa
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 575007 | Progress report | Done | Joona Marjakangas, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 575966 | Random Coding Related Tasks | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 564112 | Setup automated tests and continuous integration | Done | Joona Marjakangas
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 561786 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 564114 | Sprint retrospective | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 564117 | Sprint review | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 4 | [10 empty] | 575003 | Sprint review demo preparation | Done | Joona Marjakangas, Samuel Marisa
NeronetTrainer | Version 1 | Sprint 4 | 764199 | US18, As a user I want to be able to easily visualise variable changes by time | Done | Iiro Tähkä |  |  | 3 | 3 |  |  | 562605 | Development - Data plotting | Done | Iiro Tähkä |  | Yes | 3 | 14 | 6
NeronetTrainer | Version 1 | Sprint 4 | 764199 | US18, As a user I want to be able to easily visualise variable changes by time | Done | Iiro Tähkä |  |  | 3 | 3 |  |  | 562605 | Development - Data plotting | Done | Iiro Tähkä |  | Yes | 3 | 14 | 6
NeronetTrainer | Version 1 | Sprint 4 | 764199 | US18, As a user I want to be able to easily visualise variable changes by time | Done | Iiro Tähkä |  |  | 3 | 3 |  |  | 562603 | Development - Output format specification | Done | Iiro Tähkä |  | Yes | 3 | 14 | 6
NeronetTrainer | Version 1 | Sprint 4 | 764199 | US18, As a user I want to be able to easily visualise variable changes by time | Done | Iiro Tähkä |  |  | 3 | 3 |  |  | 562603 | Development - Output format specification | Done | Iiro Tähkä |  | Yes | 3 | 14 | 6
NeronetTrainer | Version 1 | Sprint 4 | 764199 | US18, As a user I want to be able to easily visualise variable changes by time | Done | Iiro Tähkä |  |  | 3 | 3 |  |  | 562604 | Development - Output parsing | Done | Iiro Tähkä |  | Yes | 3 | 14 | 6
NeronetTrainer | Version 1 | Sprint 4 | 764199 | US18, As a user I want to be able to easily visualise variable changes by time | Done | Iiro Tähkä |  |  | 3 | 3 |  |  | 562604 | Development - Output parsing | Done | Iiro Tähkä |  | Yes | 3 | 14 | 6
NeronetTrainer | Version 1 | Sprint 4 | 764199 | US18, As a user I want to be able to easily visualise variable changes by time | Done | Iiro Tähkä |  |  | 3 | 3 |  |  | 562606 | Documentation | Done | Iiro Tähkä |  | Yes | 3 | 14 | 6
NeronetTrainer | Version 1 | Sprint 4 | 764199 | US18, As a user I want to be able to easily visualise variable changes by time | Done | Iiro Tähkä |  |  | 3 | 3 |  |  | 562606 | Documentation | Done | Iiro Tähkä |  | Yes | 3 | 14 | 6
NeronetTrainer | Version 1 | Sprint 4 | 764199 | US18, As a user I want to be able to easily visualise variable changes by time | Done | Iiro Tähkä |  |  | 3 | 3 |  |  | 562610 | Peer Review | Done | Iiro Tähkä |  | Yes | 3 | 14 | 6
NeronetTrainer | Version 1 | Sprint 4 | 764199 | US18, As a user I want to be able to easily visualise variable changes by time | Done | Iiro Tähkä |  |  | 3 | 3 |  |  | 562610 | Peer Review | Done | Iiro Tähkä |  | Yes | 3 | 14 | 6
NeronetTrainer | Version 1 | Sprint 4 | 764199 | US18, As a user I want to be able to easily visualise variable changes by time | Done | Iiro Tähkä |  |  | 3 | 3 |  |  | 562600 | Planning | Done | Iiro Tähkä |  | Yes | 3 | 14 | 6
NeronetTrainer | Version 1 | Sprint 4 | 764199 | US18, As a user I want to be able to easily visualise variable changes by time | Done | Iiro Tähkä |  |  | 3 | 3 |  |  | 562600 | Planning | Done | Iiro Tähkä |  | Yes | 3 | 14 | 6
NeronetTrainer | Version 1 | Sprint 4 | 764199 | US18, As a user I want to be able to easily visualise variable changes by time | Done | Iiro Tähkä |  |  | 3 | 3 |  |  | 562608 | Study and installation of matplotlib | Done | Iiro Tähkä |  | Yes | 3 | 14 | 6
NeronetTrainer | Version 1 | Sprint 4 | 764199 | US18, As a user I want to be able to easily visualise variable changes by time | Done | Iiro Tähkä |  |  | 3 | 3 |  |  | 562608 | Study and installation of matplotlib | Done | Iiro Tähkä |  | Yes | 3 | 14 | 6
NeronetTrainer | Version 1 | Sprint 4 | 764199 | US18, As a user I want to be able to easily visualise variable changes by time | Done | Iiro Tähkä |  |  | 3 | 3 |  |  | 562607 | Testing | Done | Iiro Tähkä |  | Yes | 3 | 14 | 6
NeronetTrainer | Version 1 | Sprint 4 | 764199 | US18, As a user I want to be able to easily visualise variable changes by time | Done | Iiro Tähkä |  |  | 3 | 3 |  |  | 562607 | Testing | Done | Iiro Tähkä |  | Yes | 3 | 14 | 6
NeronetTrainer | Version 1 | Sprint 4 | 764163 | US19, As a maintainer, I want a clear maintenance guide | Done | Matias Pitkänen |  |  | 2 | 3 |  |  | 564111 | Embed/append mainenance instructions to the technical overview | Done |  |  | Yes | 4 | 15 | 7
NeronetTrainer | Version 1 | Sprint 4 | 764163 | US19, As a maintainer, I want a clear maintenance guide | Done | Matias Pitkänen |  |  | 2 | 3 |  |  | 564111 | Embed/append mainenance instructions to the technical overview | Done |  |  | Yes | 4 | 15 | 7
NeronetTrainer | Version 1 | Sprint 4 | 764163 | US19, As a maintainer, I want a clear maintenance guide | Done | Matias Pitkänen |  |  | 2 | 3 |  |  | 564110 | Extend and improve the documentation in the technical overview | Done |  |  | Yes | 4 | 15 | 7
NeronetTrainer | Version 1 | Sprint 4 | 764163 | US19, As a maintainer, I want a clear maintenance guide | Done | Matias Pitkänen |  |  | 2 | 3 |  |  | 564110 | Extend and improve the documentation in the technical overview | Done |  |  | Yes | 4 | 15 | 7
NeronetTrainer | Version 1 | Sprint 4 | 764163 | US19, As a maintainer, I want a clear maintenance guide | Done | Matias Pitkänen |  |  | 2 | 3 |  |  | 564107 | Improve code documentation and commenting | Done |  |  | Yes | 4 | 15 | 7
NeronetTrainer | Version 1 | Sprint 4 | 764163 | US19, As a maintainer, I want a clear maintenance guide | Done | Matias Pitkänen |  |  | 2 | 3 |  |  | 564107 | Improve code documentation and commenting | Done |  |  | Yes | 4 | 15 | 7
NeronetTrainer | Version 1 | Sprint 4 | 764160 | US20, As a user I want to have a helpful web community to help me out | Done | Joona Marjakangas |  |  | 2 | 3 |  |  | 564113 | Post an advert in Reddit | Done |  |  | Yes | 5 | 17 | 9
NeronetTrainer | Version 1 | Sprint 4 | 764160 | US20, As a user I want to have a helpful web community to help me out | Done | Joona Marjakangas |  |  | 2 | 3 |  |  | 564113 | Post an advert in Reddit | Done |  |  | Yes | 5 | 17 | 9
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 579693 | Enhance user experience based on feedback | Done | Tuomo Perä
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 579698 | Explore how plot comparison might be done | Done | Iiro Tähkä
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 581592 | General discussion and planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 577928 | Improve documentation | Done | Teemu Blomqvist
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 579897 | Learning diary | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 578415 | Refactoring and general improvements | Done
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 578379 | Review all artifacts | Done | Iiro Tähkä, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 579655 | Simo's improvement proposals | Deferred
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 576823 | Sprint planning | Done | Iiro Tähkä, Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä
NeronetTrainer | Version 1 | Sprint 5 | [10 empty] | 579654 | Sprint review | Done
NeronetTrainer | Version 1 | Sprint 5 | 780658 | As a user I want to see cluster resource info easily | Ready | Matias Pitkänen |  |  | 2 | 3 |  |  | 581588 | Choice cluster for min load | Not Started | Matias Pitkänen |  | Yes | 1 | 7 | 1
NeronetTrainer | Version 1 | Sprint 5 | 780658 | As a user I want to see cluster resource info easily | Ready | Matias Pitkänen |  |  | 2 | 3 |  |  | 581588 | Choice cluster for min load | Not Started | Matias Pitkänen |  | Yes | 1 | 7 | 1
NeronetTrainer | Version 1 | Sprint 5 | 780658 | As a user I want to see cluster resource info easily | Ready | Matias Pitkänen |  |  | 2 | 3 |  |  | 581589 | Cluster status table | Not Started | Matias Pitkänen |  | Yes | 1 | 7 | 1
NeronetTrainer | Version 1 | Sprint 5 | 780658 | As a user I want to see cluster resource info easily | Ready | Matias Pitkänen |  |  | 2 | 3 |  |  | 581589 | Cluster status table | Not Started | Matias Pitkänen |  | Yes | 1 | 7 | 1
NeronetTrainer | Version 1 | Sprint 5 | 770053 | US24: As a user, I want to cancel a submitted experiment | Done | Joona Marjakangas |  |  | 2 | 3 |  |  | 579621 | Communication between neroman and - mum | Done | Joona Marjakangas |  | Yes | 3 | 12 | 4
NeronetTrainer | Version 1 | Sprint 5 | 770053 | US24: As a user, I want to cancel a submitted experiment | Done | Joona Marjakangas |  |  | 2 | 3 |  |  | 579621 | Communication between neroman and - mum | Done | Joona Marjakangas |  | Yes | 3 | 12 | 4
NeronetTrainer | Version 1 | Sprint 5 | 770053 | US24: As a user, I want to cancel a submitted experiment | Done | Joona Marjakangas |  |  | 2 | 3 |  |  | 582497 | Improving error messages and debugging | Done | Joona Marjakangas |  | Yes | 3 | 12 | 4
NeronetTrainer | Version 1 | Sprint 5 | 770053 | US24: As a user, I want to cancel a submitted experiment | Done | Joona Marjakangas |  |  | 2 | 3 |  |  | 582497 | Improving error messages and debugging | Done | Joona Marjakangas |  | Yes | 3 | 12 | 4
NeronetTrainer | Version 1 | Sprint 5 | 770053 | US24: As a user, I want to cancel a submitted experiment | Done | Joona Marjakangas |  |  | 2 | 3 |  |  | 579591 | Planning | Done | Joona Marjakangas |  | Yes | 3 | 12 | 4
NeronetTrainer | Version 1 | Sprint 5 | 770053 | US24: As a user, I want to cancel a submitted experiment | Done | Joona Marjakangas |  |  | 2 | 3 |  |  | 579591 | Planning | Done | Joona Marjakangas |  | Yes | 3 | 12 | 4
NeronetTrainer | Version 1 | Sprint 5 | 770053 | US24: As a user, I want to cancel a submitted experiment | Done | Joona Marjakangas |  |  | 2 | 3 |  |  | 579620 | Work on communication between neromum and kids as well as between cli and neroman | Done | Joona Marjakangas |  | Yes | 3 | 12 | 4
NeronetTrainer | Version 1 | Sprint 5 | 770053 | US24: As a user, I want to cancel a submitted experiment | Done | Joona Marjakangas |  |  | 2 | 3 |  |  | 579620 | Work on communication between neromum and kids as well as between cli and neroman | Done | Joona Marjakangas |  | Yes | 3 | 12 | 4
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 579116 | Check out imports | Done | Iiro Tähkä |  | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 579116 | Check out imports | Done | Iiro Tähkä |  | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 578096 | Improve Exception handling | Done | Iiro Tähkä |  | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 578096 | Improve Exception handling | Done | Iiro Tähkä |  | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 578079 | Improve config parser config.yaml parsing | Ready | Iiro Tähkä |  | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 578079 | Improve config parser config.yaml parsing | Ready | Iiro Tähkä |  | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 578097 | Improve error messages | Not Started | Iiro Tähkä |  | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 578097 | Improve error messages | Not Started | Iiro Tähkä |  | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 578080 | Improve module importing -> Output parsing and plotting related code | Done | Iiro Tähkä |  | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 578080 | Improve module importing -> Output parsing and plotting related code | Done | Iiro Tähkä |  | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 579117 | Improve on stuff | Done | Iiro Tähkä |  | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 579117 | Improve on stuff | Done | Iiro Tähkä |  | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 578099 | Peer review | Done | Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 578099 | Peer review | Done | Joona Marjakangas, Matias Pitkänen, Samuel Marisa, Teemu Blomqvist, Tuomo Perä |  | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 578098 | Planning | Done | Iiro Tähkä |  | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 578098 | Planning | Done | Iiro Tähkä |  | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 578075 | Refactor code (Move experiment and cluster classes to modules) MAKE SURE EVERYTHING WORKS | Done | Iiro Tähkä |  | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 578075 | Refactor code (Move experiment and cluster classes to modules) MAKE SURE EVERYTHING WORKS | Done | Iiro Tähkä |  | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 578095 | Research what functions aren't safe (Don't raise exceptions when they should) | Done | Iiro Tähkä |  | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 5 | 780624 | US26: As a user I want clear feedback and messages and error handling | Done | Iiro Tähkä |  |  | 4 | 4 |  |  | 578095 | Research what functions aren't safe (Don't raise exceptions when they should) | Done | Iiro Tähkä |  | Yes | 5 | 9 | 3
NeronetTrainer | Version 1 | Sprint 6 | [10 empty] | 590220 | Export info from Agilefant to the repo | Pending | Samuel Marisa
NeronetTrainer | Version 1 | Sprint 6 | [10 empty] | 591244 | General UX improvements and refactoring | Done | Samuel Marisa
NeronetTrainer | Version 1 | Sprint 6 | [10 empty] | 590243 | General debugging, stress management and error handling | Done | Matias Pitkänen
NeronetTrainer | Version 1 | Sprint 6 | [10 empty] | 590219 | Prepare and practice the progress 3 review | Done | Joona Marjakangas
NeronetTrainer | Version 1 | Sprint 6 | [10 empty] | 591242 | Retrospective | Done | Samuel Marisa
NeronetTrainer | Version 1 | Sprint 6 | [10 empty] | 590240 | Switch rsync to scp for file transfer | Deferred | Iiro Tähkä
NeronetTrainer | Version 1 | Sprint 6 | [10 empty] | 591243 | Test session charter | Done | Samuel Marisa
NeronetTrainer | Version 1 | Sprint 6 | [10 empty] | 581584 | Update tests for travis | Done | Joona Marjakangas
NeronetTrainer | Version 1 | Sprint 6 | [10 empty] | 590245 | Updating user guide, manual and documentation | Done | Joona Marjakangas